## Sheet1
FSAM ID | FSAM Locality Name | State | Telstra 12 month RFS Date (Start date +12 Months) | Prev FSAM Ready for Service (from P6) as of 05-03-2013 | Current RFS | Current FSAM Ready for Service (from P6) as of 01-08-20132 | Current RFS Dates (Published Access Seeker Monthly RFS Date) | Initial Release RR
2ARM-01 | Armidale | NSW | 2012-11-23 | Live Site | IRRR | IRRR | 2011-04-01
2ARM-02 | Armidale | NSW | 2012-11-23 | Live Site | IRRR | IRRR | 2011-04-01
2ARM-03 | Armidale | NSW | 2012-11-23 | Live Site | IRRR | IRRR | 2011-04-01
7TRA-01 | Triabunna | TAS | 2012-11-23 | Live Site | IRRR | IRRR | 2011-04-26
5ALD-01 | Willunga | SA | 2012-11-23 | Live Site | IRRR | IRRR | 2011-05-21
3BRU-01 | Brunswick | VIC | 2012-11-23 | Live Site | IRRR | IRRR | 2011-06-01
4GUL-01 | Townsville | QLD | 2012-11-23 | Live Site | IRRR | IRRR | 2011-06-01
2KIA-01 | Kiama | NSW | 2012-11-23 | Live Site | IRRR | IRRR | 2011-07-01
7SOR-01 | Sorell | TAS | 2012-11-23 | Live Site | IRRR | IRRR | 2012-05-22
7KIN-01 | Kingston | TAS | 2012-11-23 | Live Site | IRRR | IRRR | 2012-06-12
7DEL-01 | Deloraine | TAS | 2012-11-23 | Live Site | IRRR | IRRR | 2012-06-16
7GEW-01 | George Town | TAS | 2012-11-23 | Live Site | IRRR | IRRR | 2012-06-27
3SMR-03 | South Morang | VIC | 2012-11-23 | Live Site | IRRR | IRRR | 2012-07-01
7STH-01 | St Helens | TAS | 2012-11-23 | Live Site | IRRR | IRRR | 2012-07-01
2ARM-04 | Armidale | NSW | 2012-11-23 | Live Site | IRRR | IRRR | 2012-10-02
7SCL-01 | Scottsdale | TAS | 16-Jul-10 A | Live Site | IRRR | IRRR | 2012-10-19
7SMO-01 | Smithton | TAS | 16-Jul-10 A | Live Site | IRRR | IRRR | 2012-10-19
7SOR-02 | Sorell | TAS | 16-Jul-10 A | Live Site | IRRR | IRRR | 2012-10-27
9CRC-03 | Crace | ACT | 2013-01-17 | Live Site | IRRR | IRRR | 2012-12-19
2ARM-05 | Armidale | NSW | 2013-01-17 | Live Site | IRRR | IRRR | 2012-12-22
4TOB-01 | Toowoomba | QLD | 2013-02-28 | Live Site | IRRR | IRRR | 2012-12-28
7HOB-01 | Hobart | TAS | 2013-06-02 | Live Site | IRRR | IRRR | 2012-12-31
2CFS-01 | Coffs Harbour | NSW | 2013-01-17 | Live Site | IRRR | IRRR | 2013-01-02
3SMR-02 | South Morang | VIC | 31-Mar-13 A | Live Site | IRRR | IRRR | 2013-02-22
2CFS-02 | Coffs Harbour | NSW | 2013-04-06 | Live Site | IRRR | IRRR | 2013-03-15
4APL-01 | Aspley | QLD | 2013-03-20 | Live Site | IRRR | IRRR | 2013-03-20
3BAC-02 | Bacchus Marsh | VIC | 31-Mar-13 A | Live Site | IRRR | IRRR | 2013-04-01
9CRC-01 | Crace | ACT | 28-Mar-13 A | Live Site | IRRR | IRRR | 2013-04-23
2CFS-05 | Coffs Harbour | NSW | 2013-07-01 | Live Site | SRR | SRR | 2013-05-20
4TNS-03 | Townsville | QLD | 2014-01-01 | Live Site | SRR | SRR | 2013-05-20
9CRC-02 | Crace | ACT | 29-May-13 A | Live Site | IRRR | IRRR | 2013-05-27
3BRU-03 | Brunswick | VIC | 2013-04-20 | Live Site | SRR | SRR | 2013-05-28
9CRC-04 | Crace | ACT | 2013-04-20 | Live Site | SRR | SRR | 2013-05-29
8DRW-04 | Darwin | NT | 2013-03-31 | Live Site | SRR | SRR | 2013-06-07
4AAR-02 | Acacia Ridge | QLD | 2014-04-16 | 2014-05-17 | Commenced | Commenced | 2013-06-12
4AAR-06 | Acacia Ridge | QLD | 2014-04-16 | 2014-05-17 | Commenced | Commenced | 2013-06-12
7LAU-03 | Launceston | TAS | 2013-04-20 | Live Site | SRR | SRR | 2013-06-14
7KIN-03 | Kingston | TAS | 2013-06-30 | Live Site | SRR | SRR | 2013-06-15
2SAW-02 | Sawtell | NSW | 2013-04-20 | Live Site | SRR | SRR | 2013-06-17
2SAW-03 | Sawtell | NSW | 2013-04-20 | Live Site | SRR | SRR | 2013-06-18
2PTH-02 | Penrith | NSW | 2013-10-01 | Live Site | SRR | SRR | 2013-06-19
3BAC-03 | Bacchus Marsh | VIC | 2013-04-20 | Live Site | SRR | SRR | 2013-06-19
2BLK-03 | Blacktown | NSW | 2013-04-20 | Live Site | SRR | SRR | 2013-06-20
2CFS-04 | Coffs Harbour | NSW | 2013-06-30 | Live Site | SRR | SRR | 2013-06-21
7HOB-05 | Hobart | TAS | 2013-09-30 | Live Site | SRR | SRR | 2013-06-21
3SMR-05 | South Morang | VIC | 2013-09-30 | 2013-08-08 | 2013-07-09 | 09-Jul-13 A | 2013-07-01 | SRR
4TNS-05 | Townsville | QLD | 2013-10-31 | 2013-06-29 | 2013-11-17 | 2013-11-17 | 2013-07-06 | SRR
2LID-02 | Lidcombe | NSW | 2013-04-20 | 2013-07-05 | 2013-10-13 | 2013-10-13 | 2013-07-08 | SRR
7LAU-04 | Launceston | TAS | 2013-07-01 | Live Site | SRR | SRR | 2013-07-09
3BRU-02 | Brunswick | VIC | 2013-04-20 | 2013-06-19 | 2013-08-21 | 2013-08-21 | 2013-07-15 | Commenced
2HOM-02 | Homebush | NSW | 2013-08-17 | 2013-06-16 | 2013-08-12 | 2013-08-12 | 2013-07-21 | Commenced
4TNS-01 | Townsville | QLD | 2013-04-20 | 2013-05-26 | 2013-11-17 | 2013-11-17 | 2013-07-30 | SRR
2GOS-03 | Gosford | NSW | 2013-08-13 | 2013-06-06 | 2013-08-06 | 2013-08-06 | 2013-07-30 | SRR
5ONK-01 | Onkaparinga | SA | 2013-06-30 | 2013-07-19 | 2013-08-20 | 2013-08-20 | 2013-07-30 | SRR
2LID-03 | Lidcombe | NSW | 2013-09-19 | 2013-07-04 | 2013-10-13 | 2013-10-13 | 2013-07-30 | SRR
6SPT-02 | South Perth | WA | 2013-07-27 | 2013-07-01 | 2013-09-03 | 2013-09-03 | 2013-08-01 | Commenced
2LJT-01 | Long Jetty | NSW | 2013-10-01 | 2013-08-02 | 2013-11-24 | 2013-11-24 | 2013-08-06 | SRR
4TOB-04 | Toowoomba | QLD | Live Site | RRR |  |  | 2013-08-06
4GUL-05 | Gulliver | QLD | 2013-03-31 | 2013-06-26 | 2013-10-02 | 2013-10-02 | 2013-08-17 | SRR
4GDN-03 | Goodna | QLD | 2013-07-01 | 2013-07-07 | 2014-03-31 | 2014-03-31 | 2013-08-17 | SRR
2HOM-03 | Homebush | NSW | 2013-10-14 | 2013-11-05 | 2014-01-09 | 2014-01-09 | 2013-08-17 | Commenced
4GDN-04 | Goodna | QLD | 2013-07-31 | 2013-08-03 | 2013-08-15 | 2013-08-15 | 2013-08-17 | SRR
4TNS-02 | Townsville | QLD | 2013-06-30 | 2013-06-01 | 2013-12-16 | 2013-12-16 | 2013-08-18 | SRR
4TNS-04 | Townsville | QLD | 2013-10-31 | 2013-08-28 | 2013-11-07 | 2013-11-07 | 2013-08-24 | SRR
4GDN-05 | Goodna | QLD | 2013-10-12 | 2013-08-09 | 2013-12-09 | 2013-12-09 | 2013-08-24 | SRR
2TEE-04 | Taree | NSW | 2013-11-15 | 2013-08-24 | 2014-04-04 | 2014-04-04 | 2013-08-28 | Commenced
2CFS-06 | Coffs Harbour | NSW | 2013-09-30 | 2013-07-07 | 2013-10-13 | 2013-10-13 | 2013-08-31 | SRR
3BRA-03 | Ballarat | VIC | 2013-10-31 | 2013-09-25 | 2014-05-15 | 2014-05-15 | 2013-09-01 | Commenced
3TMN-03 | Tullamarine | VIC | 2013-09-01 | 2013-12-19 | 2014-04-16 | 2014-04-16 | 2013-09-01 | Commenced
7LAU-02 | Launceston | TAS | 2013-04-20 | 2013-10-05 | 2013-11-12 | 2013-11-12 | 2013-09-01 | SRR
7HOB-06 | Hobart | TAS | 2013-09-14 | 2013-09-10 | 2013-11-23 | 2013-11-23 | 2013-09-01 | SRR
4GDN-06 | Goodna | QLD | 2013-10-12 | 2013-09-04 | 2013-12-22 | 2013-12-22 | 2013-09-01 | SRR
2LJT-03 | Long Jetty | NSW | 2013-10-01 | 2013-07-04 | 2014-01-22 | 2014-01-22 | 2013-09-03 | SRR
2RIV-02 | Riverstone | NSW | 2013-10-01 | 2013-06-21 | 2013-12-28 | 2013-12-28 | 2013-09-06 | SRR
4TOB-05 | Toowoomba | QLD | 2013-10-12 | 2013-07-28 | 2013-09-03 | 2013-09-03 | 2013-09-07 | Commenced
4MKY-01 | Mackay | QLD | 2013-08-17 | 2013-07-17 | 2013-09-02 | 2013-09-02 | 2013-09-07 | SRR
2PTH-04 | Penrith | NSW | 2013-10-24 | 2013-07-31 | 2013-09-28 | 2013-09-28 | 2013-09-14 | SRR
2BLK-04 | Blacktown | NSW | 2013-07-01 | 2013-06-13 | 2013-11-03 | 2013-11-03 | 2013-09-17 | SRR
2PTH-03 | Penrith | NSW | 2013-10-12 | 2013-08-04 | 2013-12-14 | 2013-12-14 | 2013-09-17 | SRR
2WLG-01 | Wollongong | NSW | 2013-10-12 | 2013-09-12 | 2013-11-29 | 2013-11-29 | 2013-09-27 | SRR
4MKY-02 | Mackay | QLD | 2013-09-14 | 2013-07-12 | 2013-11-16 | 2013-11-16 | 2013-09-28 | SRR
2LJT-02 | Long Jetty | NSW | 2013-10-01 | 2013-07-07 | 2014-01-29 | 2014-01-29 | 2013-09-28 | SRR
2TEE-03 | Taree | NSW | 2013-11-15 | 2013-09-29 | 2014-03-30 | 2014-03-30 | 2013-09-28 | Not started
3BRA-01 | Ballarat | VIC | 2013-04-30 | 2013-07-14 | 2013-12-03 | 2013-12-03 | 2013-09-30 | Commenced
3BRU-05 | Brunswick | VIC | 2013-09-30 | 2013-10-03 | 2013-08-24 | 2013-08-24 | 2013-09-30 | SRR
4ACO-02 | Ascot | QLD | 2013-10-12 | 2013-06-30 | 2014-04-10 | 2014-04-10 | 2013-09-30 | SRR
4NDG-03 | Nudgee | QLD | 2013-10-12 | 2013-10-09 | 2013-10-16 | 2013-10-16 | 2013-10-01 | Commenced
4ACO-04 | Ascot | QLD | 2013-10-12 | 2013-08-02 | 2014-03-27 | 2014-03-27 | 2013-10-01 | Commenced
3TMN-02 | Tullamarine | VIC | 2013-09-02 | 2013-12-19 | 2013-12-27 | 2013-12-27 | 2013-10-01 | Commenced
4TOB-06 | Toowoomba | QLD | 2013-10-23 | 2013-09-21 | 2014-01-04 | 2014-01-04 | 2013-10-01 | Commenced
2LID-05 | Lidcombe | NSW | 2013-12-14 | 2013-10-05 | 2014-02-20 | 2014-02-20 | 2013-10-01 | Commenced
2LJT-07 | Long Jetty | NSW | 2013-12-14 | 2013-10-20 | 2014-05-23 | 2014-05-23 | 2013-10-01 | Commenced
2GOS-05 | Gosford | NSW | 2013-12-14 | 2013-10-26 | 2014-04-04 | 2014-04-04 | 2013-10-01 | Commenced
4CAI-02 | Cairns | QLD | 2013-10-31 | 2013-10-17 | 2014-02-08 | 2014-02-08 | 2013-10-01 | Commenced
7BEV-01 | Bellerive | TAS | 2013-09-30 | 2013-06-30 | 2013-09-28 | 2013-09-28 | 2013-10-01 | Commenced
2CFS-07 | Coffs Harbour | NSW | 2013-10-12 | 2013-10-20 | 2013-11-09 | 2013-11-09 | 2013-10-01 | Commenced
4CAI-03 | Cairns | QLD | 2013-11-01 | 2013-10-17 | 2013-12-11 | 2013-12-11 | 2013-10-01 | Commenced
2LID-04 | Lidcombe | NSW | 2013-12-18 | 2013-09-29 | 2014-03-26 | 2014-03-26 | 2013-10-01 | Commenced
2GOS-07 | Gosford | NSW | 2013-11-15 | 2013-10-18 | 2014-05-16 | 2014-05-16 | 2013-10-01 | Commenced
3TMN-01 | Tullamarine | VIC | 2013-09-05 | 2013-12-19 | 2014-04-23 | 2014-04-23 | 2013-10-01 | Commenced
4ACO-03 | Ascot | QLD | 2013-10-12 | 2013-08-01 | 2014-04-03 | 2014-04-03 | 2013-10-01 | Commenced
4MKY-03 | Mackay | QLD | 2013-11-01 | 2013-10-02 | 2014-01-26 | 2014-01-26 | 2013-10-01 | Commenced
4IPS-02 | Ipswich | QLD | 2013-11-15 | 2013-10-13 | 2014-01-09 | 2014-01-09 | 2013-10-01 | Commenced
3MLT-07 | Melton | VIC | 2013-08-31 | 2013-11-29 | 2014-05-27 | 2014-05-27 | 2013-10-01 | Commenced
6MSP-03 | Meadow Springs | WA | 2014-01-31 | 2013-06-05 | 2013-09-12 | 2013-09-12 | 2013-10-01 | SRR
2SAW-04 | Sawtell | NSW | 2013-07-31 | 2013-06-08 | 2013-09-22 | 2013-09-22 | 2013-10-01 | SRR
3CTN-04 | Carlton | VIC | 2013-11-01 | 2013-10-12 | 2013-10-16 | 2013-10-16 | 2013-10-01 | SRR
3CTN-07 | Carlton | VIC | 2013-11-01 | 2013-07-24 | 2013-10-16 | 2013-10-16 | 2013-10-01 | SRR
7HOB-03 | Hobart | TAS | 2013-06-30 | 2013-10-16 | 2013-10-16 | 2013-10-16 | 2013-10-01 | SRR
3BRU-04 | Brunswick | VIC | 2013-08-01 | 2013-08-08 | 2013-11-08 | 2013-11-08 | 2013-10-01 | SRR
5SFD-04 | Seaford | SA | 2013-10-31 | 2013-06-30 | 2013-11-09 | 2013-11-09 | 2013-10-01 | SRR
7KIN-02 | Kingston | TAS | 2013-09-30 | 2013-09-21 | 2013-12-07 | 2013-12-07 | 2013-10-01 | SRR
3BRU-06 | Brunswick | VIC | 2013-09-30 | 2013-10-11 | 2013-12-10 | 2013-12-10 | 2013-10-01 | SRR
5ALD-03 | Aldinga | SA | 2013-06-30 | 2013-09-22 | 2013-12-11 | 2013-12-11 | 2013-10-01 | SRR
7SOE-01 | Somerset | TAS | 2013-07-01 | 2013-08-18 | 2013-12-27 | 2013-12-27 | 2013-10-01 | SRR
2RIV-04 | Riverstone | NSW | 2013-11-15 | 2013-09-19 | 2014-02-11 | 2014-02-11 | 2013-10-01 | SRR
4AAR-01 | Not Published to Access Seeker | QLD | 2014-07-16 | Not started |  |  | 2013-10-24 | 2013-11-23
2MIR-01 | Not Published to Access Seeker | NSW | 2014-07-18 | Not started |  |  | 2013-10-26 | 2013-11-25
5MTB-01 | Not Published to Access Seeker | SA | 2014-07-19 | Not started |  |  | 2013-10-27 | 2013-11-26
6CGE-01 | Not Published to Access Seeker | WA | 2014-07-19 | Not started |  |  | 2013-10-27 | 2013-11-26
2BAO-01 | Not Published to Access Seeker | NSW | 2014-07-22 | Not started |  |  | 2013-10-30 | 2013-11-29
5MTB-02 | Not Published to Access Seeker | SA | 2014-07-22 | Not started |  |  | 2013-10-30 | 2013-11-29
5SFD-01 | Seaford | SA | 2013-07-31 | 2013-10-02 | 2013-12-14 | 2013-12-14 | 2013-11-01 | Commenced
4KLG-01 | Kallangur and Petrie | QLD | 2013-10-12 | 2013-11-04 | 2014-01-22 | 2014-01-22 | 2013-11-01 | Commenced
3BRA-04 | Ballarat | VIC | 2013-12-01 | 2013-11-16 | 2014-04-24 | 2014-04-24 | 2013-11-01 | Commenced
3MLT-08 | Melton | VIC | 2013-10-30 | 2013-11-29 | 2014-02-07 | 2014-02-07 | 2013-11-01 | Commenced
4GUL-06 | Gulliver | QLD | 2013-09-30 | 2013-11-28 | 2013-12-17 | 2013-12-17 | 2013-11-01 | Commenced
2WLG-02 | Wollongong | NSW | 2013-10-12 | 2013-09-28 | 2014-05-07 | 2014-05-07 | 2013-11-01 | Commenced
2GOS-04 | Gosford | NSW | 2013-10-12 | 2013-11-21 | 2014-02-16 | 2014-02-16 | 2013-11-01 | Commenced
2TEE-02 | Taree | NSW | 2013-11-01 | 2013-11-10 | 2014-04-19 | 2014-04-19 | 2013-11-01 | Commenced
3BRA-02 | Ballarat | VIC | 2013-07-01 | 2013-11-10 | 2013-11-29 | 2013-11-29 | 2013-11-01 | Commenced
2GOS-06 | Gosford | NSW | 2013-10-14 | 2013-10-04 | 2013-12-06 | 2013-12-06 | 2013-11-01 | Commenced
4BDB-01 | Bundamba | QLD | 2013-12-14 | 2013-10-06 | 2014-03-02 | 2014-03-02 | 2013-11-01 | Commenced
4TNS-06 | Townsville | QLD | 2013-12-01 | 2013-11-01 | 2014-04-19 | 2014-04-19 | 2013-11-01 | Commenced
4KLG-04 | Kallangur and Petrie | QLD | 2013-12-14 | 2013-10-24 | 2014-03-30 | 2014-03-30 | 2013-11-01 | Commenced
4IPS-04 | Ipswich | QLD | 2014-02-05 | 2014-01-23 | 2014-03-09 | 2014-03-09 | 2013-11-01 | Commenced
4NDG-01 | Nudgee | QLD | 2013-08-13 | 2013-11-01 | 2013-12-26 | 2013-12-26 | 2013-11-01 | SRR
7KIN-04 | Kingston | TAS | 2013-09-02 | 2013-10-16 | 2013-12-27 | 2013-12-27 | 2013-11-01 | SRR
5ALD-02 | Aldinga | SA | 2013-06-30 | 2013-11-01 | 2014-01-25 | 2014-01-25 | 2013-11-01 | SRR
2DAP-01 | Dapto | NSW | 2014-01-24 | 2013-10-12 | 2014-03-19 | 2014-03-19 | 2013-11-01 | Not started
2RCH-05 | Richmond | NSW | 2013-10-12 | 2013-08-11 | 2014-03-30 | 2014-03-30 | 2013-11-01 | SRR
4GDN-07 | Goodna | QLD | 2013-11-15 | 2013-10-10 | 2014-04-12 | 2014-04-12 | 2013-11-01 | Not started
2MIR-02 | Not Published to Access Seeker | NSW | 2014-08-21 | Not started |  |  | 2013-11-29 | 2013-12-29
7KIN-05 | Kingston | TAS | 2013-12-01 | 2013-11-29 | 2014-01-01 | 2014-01-01 | 2013-12-01 | Commenced
3TMN-04 | Tullamarine | VIC | 2013-12-01 | 2013-12-19 | 2014-03-29 | 2014-03-29 | 2013-12-01 | Commenced
3TMN-05 | Tullamarine | VIC | 2013-12-01 | 2013-12-19 | 2014-04-16 | 2014-04-16 | 2013-12-01 | Commenced
7LAU-05 | Launceston | TAS | 2013-10-12 | 2013-12-11 | 2014-02-15 | 2014-02-15 | 2013-12-01 | Commenced
2COR-11 | Corrimal | NSW | 2014-04-01 | 2014-03-01 | 2014-05-09 | 2014-05-09 | 2013-12-01 | Commenced
3CTN-01 | Carlton | VIC | 2013-12-14 | 2013-12-04 | 2014-04-03 | 2014-04-03 | 2013-12-01 | Commenced
3SMR-07 | South Morang | VIC | 2014-02-18 | 2013-12-20 | 2014-05-13 | 2014-05-13 | 2013-12-01 | Commenced
2BLK-06 | Blacktown | NSW | 2013-12-14 | 2013-09-26 | 2014-01-08 | 2014-01-08 | 2013-12-01 | Commenced
2DAP-02 | Dapto | NSW | 2013-10-12 | 2013-09-26 | 2013-11-30 | 2013-11-30 | 2013-12-01 | SRR
2DAP-03 | Dapto | NSW | 2013-12-01 | 2013-09-29 | 2014-01-23 | 2014-01-23 | 2013-12-01 | SRR
3SMR-06 | South Morang | VIC | 2013-10-30 | 2013-11-10 | 2014-03-01 | 2014-03-01 | 2013-12-01 | SRR
4APL-05 | Aspley | QLD | 2013-12-06 | 2013-11-17 | 2014-03-23 | 2014-03-23 | 2013-12-01 | Not started
2DAP-06 | Dapto | NSW | 2014-01-24 | 2013-11-13 | 2014-05-05 | 2014-05-05 | 2013-12-01 | Not started
2LJT-04 | Long Jetty | NSW | 2013-08-14 | 2013-12-20 | 2014-06-06 | 2014-06-06 | 2013-12-01 | Not started
2DAP-05 | Dapto | NSW | 2013-12-14 | 2013-10-26 | 2014-06-26 | 2014-06-26 | 2013-12-01 | Not started
3MLT-06 | Melton | VIC | 2013-10-12 | 2013-11-29 | 2014-08-15 | 2014-08-15 | 2013-12-01 | Not started
2CAM-04 | Not Published to Access Seeker | NSW | 2014-09-21 | Not started |  |  | 2013-12-30 | 2014-01-29
2HEN-01 | Not Published to Access Seeker | NSW | 2014-09-21 | Not started |  |  | 2013-12-30 | 2014-01-29
4SHF-01 | Not Published to Access Seeker | QLD | 2015-02-25 | Not started |  |  | 2013-12-30 | 2014-01-29
5MTB-03 | Not Published to Access Seeker | SA | 2014-09-21 | Not started |  |  | 2013-12-30 | 2014-01-29
4NDG-02 | Nudgee | QLD | 2013-10-12 | 2013-09-11 | 2013-12-27 | 2013-12-27 | 2014-01-01 | Commenced
2RCH-06 | Richmond | NSW | 2013-10-12 | 2013-09-26 | 2014-02-01 | 2014-02-01 | 2014-01-01 | Commenced
2WLG-04 | Wollongong | NSW | 2014-02-19 | 2013-10-06 | 2014-05-30 | 2014-05-30 | 2014-01-01 | Commenced
6MDR-03 | Mandurah | WA | 2013-06-30 | 2013-08-09 | 2013-12-27 | 2013-12-27 | 2014-01-01 | SRR
4ROT-01 | Rockhampton | QLD | 2013-12-27 | 2013-12-25 | 2014-03-23 | 2014-03-23 | 2014-01-01 | Not started
2LID-07 | Lidcombe | NSW | 2014-01-24 | 2013-11-10 | 2014-04-03 | 2014-04-03 | 2014-01-01 | Not started
2HOM-04 | Homebush | NSW | 2014-01-24 | 2013-12-05 | 2014-04-10 | 2014-04-10 | 2014-01-01 | Not started
2RIV-03 | Riverstone | NSW | 2013-09-14 | 2013-07-07 | 2014-04-10 | 2014-04-10 | 2014-01-01 | SRR
2COR-05 | Corrimal | NSW | 2014-03-01 | 2014-03-01 | 2014-04-14 | 2014-04-14 | 2014-01-01 | Not started
2BLK-05 | Blacktown | NSW | 2013-10-21 | 2013-07-19 | 2014-04-17 | 2014-04-17 | 2014-01-01 | SRR
2WLG-03 | Wollongong | NSW | 2013-12-14 | 2013-10-19 | 2014-05-02 | 2014-05-02 | 2014-01-01 | Not started
3TMN-07 | Tullamarine | VIC | 2014-01-03 | 2014-01-05 | 2014-05-15 | 2014-05-15 | 2014-01-01 | Not started
3BRA-05 | Ballarat | VIC | 2013-12-19 | 2013-12-06 | 2014-05-20 | 2014-05-20 | 2014-01-01 | Not started
2COR-07 | Corrimal | NSW | 2014-03-01 | 2014-03-01 | 2014-05-21 | 2014-05-21 | 2014-01-01 | Not started
2BGR-01 | Not Published to Access Seeker | NSW | 2014-10-21 | Not started |  |  | 2014-01-29 | 2014-02-28
2KOO-01 | Not Published to Access Seeker | NSW | 2014-10-21 | Not started |  |  | 2014-01-29 | 2014-02-28
2MIR-03 | Not Published to Access Seeker | NSW | 2014-10-21 | Not started |  |  | 2014-01-29 | 2014-02-28
2NRL-01 | Not Published to Access Seeker | NSW | 2014-10-21 | Not started |  |  | 2014-01-29 | 2014-02-28
3KAL-07 | Not Published to Access Seeker | VIC | 2014-10-20 | Not started |  |  | 2014-01-29 | 2014-02-28
4IPS-01 | Not Published to Access Seeker | QLD | 2014-10-21 | Not started |  |  | 2014-01-29 | 2014-02-28
5MOD-12 | Not Published to Access Seeker | SA | 2014-10-21 | Not started |  |  | 2014-01-29 | 2014-02-28
7LAU-06 | Launceston | TAS | 2013-11-15 | 2014-01-01 | 2013-12-28 | 2013-12-28 | 2014-02-01 | Commenced
6GLT-03 | Geraldton | WA | 2013-06-30 | 2013-10-30 | 2014-03-14 | 2014-03-14 | 2014-02-01 | Commenced
3MLT-09 | Melton | VIC | 2014-03-01 | 2013-11-29 | 2014-05-10 | 2014-05-10 | 2014-02-01 | Commenced
6APP-02 | Applecross | WA | 2013-07-01 | 2013-08-08 | 2013-12-25 | 2013-12-25 | 2014-02-01 | Commenced
5PTE-01 | Port Elliot and Victor Harbour | SA | 2014-12-01 | 2013-12-25 | 2014-07-02 | 2014-07-02 | 2014-02-01 | Commenced
8CSU-04 | Casuarina | NT | 2013-10-12 | 2013-12-11 | 2014-03-16 | 2014-03-16 | 2014-02-01 | Commenced
3MLT-02 | Melton | VIC | 2014-02-06 | 2014-01-24 | 2014-04-26 | 2014-04-26 | 2014-02-01 | Commenced
8CSU-05 | Casuarina | NT | 2013-12-14 | 2013-12-29 | 2014-04-10 | 2014-04-10 | 2014-02-01 | Commenced
6SPT-01 | South Perth | WA | 2013-06-27 | 2013-12-07 | 2014-05-03 | 2014-05-03 | 2014-02-01 | Commenced
6APP-01 | Applecross | WA | 2013-06-30 | 2013-12-12 | 2014-03-05 | 2014-03-05 | 2014-02-01 | Commenced
8CSU-03 | Casuarina | NT | 2014-09-28 | 2013-11-03 | 2014-02-04 | 2014-02-04 | 2014-02-01 | SRR
6MSP-01 | Meadow Springs | WA | 2013-07-01 | 2013-11-10 | 2014-02-14 | 2014-02-14 | 2014-02-01 | SRR
8DRW-05 | Darwin | NT | 2013-08-17 | 2013-06-15 | 2014-04-23 | 2014-04-23 | 2014-02-01 | SRR
8DRW-06 | Darwin | NT | 2013-10-12 | 2013-06-16 | 2014-04-23 | 2014-04-23 | 2014-02-01 | SRR
2DAP-04 | Dapto | NSW | 2013-12-01 | 2013-09-18 | 2014-04-26 | 2014-04-26 | 2014-02-01 | SRR
3BRA-06 | Ballarat | VIC | 2013-11-15 | 2013-12-12 | 2014-05-15 | 2014-05-15 | 2014-02-01 | Not started
4ACO-01 | Ascot | QLD | 2013-10-12 | 2013-06-29 | 2014-05-17 | 2014-05-17 | 2014-02-01 | SRR
3CTN-06 | Carlton | VIC | 2013-11-01 | 2013-12-08 | 2014-07-09 | 2014-07-09 | 2014-02-01 | Not started
2MDG-01 | Mudgee | NSW | 2014-03-20 | 2014-07-01 | 2014-09-23 | 2014-09-23 | 2014-02-01 | Not started
2MDG-02 | Mudgee | NSW | 2014-03-20 | 2014-07-01 | 2014-09-23 | 2014-09-23 | 2014-02-01 | Not started
2MDG-03 | Mudgee | NSW | 2014-02-01 | 2014-07-01 | 2014-09-23 | 2014-09-23 | 2014-02-01 | Not started
6PNJ-01 | Pinjarra | WA | 2013-07-01 | 2014-02-08 | 2014-05-08 | 2014-05-08 | 2014-03-01 | Commenced
6GLT-05 | Geraldton | WA | 2013-11-30 | 2013-11-22 | 2014-06-11 | 2014-06-11 | 2014-03-01 | Commenced
8CSU-01 | Casuarina | NT | 2014-09-30 | 2013-12-29 | 2014-02-15 | 2014-02-15 | 2014-03-01 | Commenced
5PRO-03 | Prospect | SA | 2013-10-12 | 2014-01-31 | 2014-07-09 | 2014-07-09 | 2014-03-01 | Commenced
2LID-06 | Lidcombe | NSW | 2013-12-14 | 2014-01-08 | 2014-03-26 | 2014-03-26 | 2014-03-01 | Commenced
5MOD-03 | Modbury | SA | 2013-03-31 | 2014-01-30 | 2014-04-23 | 2014-04-23 | 2014-03-01 | Commenced
5SBY-01 | Strathalbyn | SA | 2013-09-30 | 2014-02-13 | 2014-05-24 | 2014-05-24 | 2014-03-01 | Commenced
8DRW-07 | Darwin | NT | 2013-10-20 | 2013-12-15 | 2014-05-02 | 2014-05-02 | 2014-03-01 | Commenced
4ROT-03 | Rockhampton | QLD | 2013-12-19 | 2014-02-01 | 2014-03-30 | 2014-03-30 | 2014-03-01 | Not started
2COR-06 | Corrimal | NSW | 2014-03-01 | 2014-03-01 | 2014-05-04 | 2014-05-04 | 2014-03-01 | Not started
6VIC-06 | Victoria Park | WA | 2013-12-01 | 2014-01-29 | 2014-05-29 | 2014-05-29 | 2014-03-01 | Not started
5YKL-01 | Yankalilla | SA | 2013-11-01 | 2014-01-26 | 2014-08-01 | 2014-08-01 | 2014-03-01 | Not started
2STL-01 | Not Published to Access Seeker | NSW | 2014-11-21 | Not started |  |  | 2014-03-01 | 2014-03-31
2WGL-01 | Not Published to Access Seeker | NSW | 2014-11-21 | Not started |  |  | 2014-03-01 | 2014-03-31
3KEW-01 | Not Published to Access Seeker | VIC | 2014-11-20 | Not started |  |  | 2014-03-01 | 2014-03-31
4AAR-03 | Not Published to Access Seeker | QLD | 2014-11-21 | Not started |  |  | 2014-03-01 | 2014-03-31
4WUR-01 | Not Published to Access Seeker | QLD | 2016-08-13 | Not started |  |  | 2014-03-01 | 2014-03-31
5PRO-06 | Prospect | SA | 2013-12-14 | 2014-03-02 | 2014-06-19 | 2014-06-19 | 2014-04-01 | Commenced
5PRO-02 | Prospect | SA | 2013-06-01 | 2014-02-27 | 2014-06-19 | 2014-06-19 | 2014-04-01 | Commenced
6APP-03 | Applecross | WA | 2013-10-31 | 2014-01-03 | 2014-04-12 | 2014-04-12 | 2014-04-01 | Commenced
5SFD-02 | Seaford | SA | 2013-10-31 | 2014-03-06 | 2014-04-16 | 2014-04-16 | 2014-04-01 | Commenced
6VIC-05 | Victoria Park | WA | 2013-09-14 | 2014-02-15 | 2014-07-26 | 2014-07-26 | 2014-04-01 | Commenced
6MDR-04 | Mandurah | WA | 2013-06-30 | 2013-12-18 | 2014-05-10 | 2014-05-10 | 2014-04-01 | Commenced
2LJT-05 | Long Jetty | NSW | 2014-04-01 | 2014-02-20 | 2014-04-24 | 2014-04-24 | 2014-04-01 | Not started
6SPT-05 | South Perth | WA | 2013-12-14 | 2014-02-21 | 2014-05-14 | 2014-05-14 | 2014-04-01 | Not started
6VIC-08 | Victoria Park | WA | 2014-04-04 | 2014-03-15 | 2014-05-29 | 2014-05-29 | 2014-04-01 | Not started
6GLT-06 | Geraldton | WA | 2014-01-01 | 2014-01-25 | 2014-06-19 | 2014-06-19 | 2014-04-01 | Not started
6GLT-07 | Geraldton | WA | 2014-03-05 | 2013-12-20 | 2014-06-19 | 2014-06-19 | 2014-04-01 | Not started
6APP-05 | Applecross | WA | 2014-02-04 | 2014-03-02 | 2014-06-27 | 2014-06-27 | 2014-04-01 | Not started
2TEE-01 | Taree | NSW | 2013-10-12 | 2013-10-19 | 2014-08-01 | 2014-08-01 | 2014-04-01 | Not started
5MOD-06 | Modbury | SA | 2013-11-15 | 2014-03-21 | 2014-08-29 | 2014-08-29 | 2014-04-01 | Not started
2CAM-05 | Not Published to Access Seeker | NSW | 2014-12-22 | Not started |  |  | 2014-04-01 | 2014-05-01
2TAM-04 | Not Published to Access Seeker | NSW | 2014-12-22 | Not started |  |  | 2014-04-01 | 2014-05-01
2WGL-02 | Not Published to Access Seeker | NSW | 2014-12-22 | Not started |  |  | 2014-04-01 | 2014-05-01
3KEW-02 | Not Published to Access Seeker | VIC | 2014-12-21 | Not started |  |  | 2014-04-01 | 2014-05-01
3NBA-02 | Not Published to Access Seeker | VIC | 2014-12-21 | Not started |  |  | 2014-04-01 | 2014-05-01
4AVO-01 | Not Published to Access Seeker | QLD | 2020-03-13 | Not started |  |  | 2014-04-01 | 2014-05-01
4WUR-02 | Not Published to Access Seeker | QLD | 2016-08-13 | Not started |  |  | 2014-04-01 | 2014-05-01
5MTB-04 | Not Published to Access Seeker | SA | 2014-12-22 | Not started |  |  | 2014-04-01 | 2014-05-01
6APP-11 | Not Published to Access Seeker | WA | 2014-12-22 | Not started |  |  | 2014-04-01 | 2014-05-01
6HOP-01 | Not Published to Access Seeker | WA | 2014-12-22 | Not started |  |  | 2014-04-01 | 2014-05-01
2COR-01 | Not Published to Access Seeker | NSW | 2015-01-19 | Not started |  |  | 2014-04-29 | 2014-05-29
2NRL-02 | Not Published to Access Seeker | NSW | 2015-01-19 | Not started |  |  | 2014-04-29 | 2014-05-29
4WUR-03 | Not Published to Access Seeker | QLD | 2016-08-13 | Not started |  |  | 2014-04-29 | 2014-05-29
6PNJ-02 | Pinjarra | WA | 2013-11-30 | 2013-12-11 | 2014-04-20 | 2014-04-20 | 2014-05-01 | Commenced
5ALD-04 | Aldinga | SA | 2013-09-14 | 2014-02-20 | 2014-04-13 | 2014-04-13 | 2014-05-01 | Commenced
7LAU-07 | Launceston | TAS | 2013-12-14 | 2014-04-16 | 2014-03-08 | 2014-03-08 | 2014-05-01 | Commenced
5PTE-03 | Port Elliot and Victor Harbour | SA | 2014-12-10 | 2014-04-05 | 2014-06-11 | 2014-06-11 | 2014-05-01 | Commenced
5PRO-05 | Prospect | SA | 2013-11-28 | 2014-03-21 | 2014-12-18 | 2014-12-18 | 2014-05-01 | Commenced
6SPT-06 | South Perth | WA | 2013-12-19 | 2014-03-20 | 2014-05-02 | 2014-05-02 | 2014-05-01 | Not started
6NTH-01 | Northampton | WA | 2014-04-15 | 2014-04-02 | 2014-05-28 | 2014-05-28 | 2014-05-01 | Not started
6CGE-03 | South Coogee | WA | 2013-12-14 | 2014-04-04 | 2014-06-21 | 2014-06-21 | 2014-05-01 | Not started
2ADL-01 | Not Published to Access Seeker | NSW | 2015-02-19 | Not started |  |  | 2014-05-30 | 2014-06-29
4AAR-04 | Not Published to Access Seeker | QLD | 2015-02-19 | Not started |  |  | 2014-05-30 | 2014-06-29
4KLG-02 | Not Published to Access Seeker | QLD | 2015-02-19 | Not started |  |  | 2014-05-30 | 2014-06-29
6RKH-01 | Not Published to Access Seeker | WA | 2015-02-19 | Not started |  |  | 2014-05-30 | 2014-06-29
7CAM-01 | Not Published to Access Seeker | TAS | 2015-03-28 | Not started |  |  | 2014-05-30 | 2014-06-29
6MSP-02 | Meadow Springs | WA | 2013-11-01 | 2013-12-05 | 2014-08-08 | 2014-08-08 | 2014-06-01 | Commenced
6GLT-04 | Geraldton | WA | 2013-10-14 | 2013-11-30 | 2014-05-16 | 2014-05-16 | 2014-06-01 | Commenced
6APP-04 | Applecross | WA | 2013-12-01 | 2013-12-13 | 2014-04-20 | 2014-04-20 | 2014-06-01 | Not started
6MDR-07 | Mandurah | WA | 2014-03-21 | 2014-02-09 | 2014-07-13 | 2014-07-13 | 2014-06-01 | Not started
2HOL-01 | Not Published to Access Seeker | NSW | 2015-03-21 | Not started |  |  | 2014-06-29 | 2014-07-29
2MIR-04 | Not Published to Access Seeker | NSW | 2015-03-21 | Not started |  |  | 2014-06-29 | 2014-07-29
2WGL-03 | Not Published to Access Seeker | NSW | 2015-03-21 | Not started |  |  | 2014-06-29 | 2014-07-29
3HAW-01 | Not Published to Access Seeker | VIC | 2015-03-20 | Not started |  |  | 2014-06-29 | 2014-07-29
4AAR-05 | Not Published to Access Seeker | QLD | 2015-03-21 | Not started |  |  | 2014-06-29 | 2014-07-29
4CNS-01 | Not Published to Access Seeker | QLD | 2015-03-21 | Not started |  |  | 2014-06-29 | 2014-07-29
4MTM-01 | Not Published to Access Seeker | QLD | 2015-03-21 | Not started |  |  | 2014-06-29 | 2014-07-29
4SHF-02 | Not Published to Access Seeker | QLD | 2015-03-21 | Not started |  |  | 2014-06-29 | 2014-07-29
5MTB-05 | Not Published to Access Seeker | SA | 2015-03-21 | Not started |  |  | 2014-06-29 | 2014-07-29
6RKH-02 | Not Published to Access Seeker | WA | 2015-03-21 | Not started |  |  | 2014-06-29 | 2014-07-29
3KEW-03 | Not Published to Access Seeker | VIC | 2015-03-27 | Not started |  |  | 2014-07-06 | 2014-08-05
2CBT-05 | Not Published to Access Seeker | NSW | 2015-04-21 | Not started |  |  | 2014-07-30 | 2014-08-29
2CUL-01 | Not Published to Access Seeker | NSW | 2015-04-21 | Not started |  |  | 2014-07-30 | 2014-08-29
2STL-02 | Not Published to Access Seeker | NSW | 2015-04-21 | Not started |  |  | 2014-07-30 | 2014-08-29
2TAM-05 | Not Published to Access Seeker | NSW | 2015-04-21 | Not started |  |  | 2014-07-30 | 2014-08-29
3TNB-01 | Not Published to Access Seeker | VIC | 2015-04-20 | Not started |  |  | 2014-07-30 | 2014-08-29
4WOT-01 | Not Published to Access Seeker | QLD | 2015-04-21 | Not started |  |  | 2014-07-30 | 2014-08-29
7CAM-02 | Not Published to Access Seeker | TAS | 2015-03-28 | Not started |  |  | 2014-07-30 | 2014-08-29
9QBN-08 | Not Published to Access Seeker | ACT | 2015-04-21 | Not started |  |  | 2014-07-30 | 2014-08-29
3NBA-03 | Not Published to Access Seeker | VIC | 2015-04-26 | Not started |  |  | 2014-08-05 | 2014-09-04
2MOS-04 | Not Published to Access Seeker | NSW | 2015-05-21 | Not started |  |  | 2014-08-29 | 2014-09-28
2NRL-03 | Not Published to Access Seeker | NSW | 2015-05-21 | Not started |  |  | 2014-08-29 | 2014-09-28
4LAM-01 | Not Published to Access Seeker | QLD | 2015-05-21 | Not started |  |  | 2014-08-29 | 2014-09-28
4SHF-03 | Not Published to Access Seeker | QLD | 2015-05-21 | Not started |  |  | 2014-08-29 | 2014-09-28
4WUR-04 | Not Published to Access Seeker | QLD | 2016-08-13 | Not started |  |  | 2014-08-29 | 2014-09-28
5GUG-01 | Not Published to Access Seeker | SA | 2017-12-27 | Not started |  |  | 2014-08-29 | 2014-09-28
6RKH-03 | Not Published to Access Seeker | WA | 2015-05-21 | Not started |  |  | 2014-08-29 | 2014-09-28
7CAM-03 | Not Published to Access Seeker | TAS | 2015-03-28 | Not started |  |  | 2014-08-29 | 2014-09-28
3HAW-02 | Not Published to Access Seeker | VIC | 2015-05-27 | Not started |  |  | 2014-09-05 | 2014-10-05
2CBT-06 | Not Published to Access Seeker | NSW | 2015-06-21 | Not started |  |  | 2014-09-29 | 2014-10-29
2TAM-06 | Not Published to Access Seeker | NSW | 2015-06-21 | Not started |  |  | 2014-09-29 | 2014-10-29
3BAY-03 | Not Published to Access Seeker | VIC | 2015-06-20 | Not started |  |  | 2014-09-29 | 2014-10-29
3DAD-03 | Not Published to Access Seeker | VIC | 2015-06-20 | Not started |  |  | 2014-09-29 | 2014-10-29
3WSE-01 | Not Published to Access Seeker | VIC | 2015-06-20 | Not started |  |  | 2014-09-29 | 2014-10-29
4CHR-01 | Not Published to Access Seeker | QLD | 2015-06-21 | Not started |  |  | 2014-09-29 | 2014-10-29
4LAM-02 | Not Published to Access Seeker | QLD | 2015-06-21 | Not started |  |  | 2014-09-29 | 2014-10-29
4NEW-04 | Not Published to Access Seeker | QLD | 2015-06-21 | Not started |  |  | 2014-09-29 | 2014-10-29
6ESP-01 | Not Published to Access Seeker | WA | 2015-06-21 | Not started |  |  | 2014-09-29 | 2014-10-29
6MLO-04 | Not Published to Access Seeker | WA | 2015-06-21 | Not started |  |  | 2014-09-29 | 2014-10-29
9KBA-04 | Not Published to Access Seeker | ACT | 2015-06-21 | Not started |  |  | 2014-09-29 | 2014-10-29
9QBN-09 | Not Published to Access Seeker | ACT | 2015-06-21 | Not started |  |  | 2014-09-29 | 2014-10-29
2BWL-01 | Not Published to Access Seeker | NSW | 2015-06-27 | Not started |  |  | 2014-10-05 | 2014-11-04
2MIR-05 | Not Published to Access Seeker | NSW | 2015-06-27 | Not started |  |  | 2014-10-05 | 2014-11-04
2STL-03 | Not Published to Access Seeker | NSW | 2015-06-27 | Not started |  |  | 2014-10-05 | 2014-11-04
2SUX-01 | Not Published to Access Seeker | NSW | 2015-06-27 | Not started |  |  | 2014-10-05 | 2014-11-04
2URG-01 | Not Published to Access Seeker | NSW | 2015-09-23 | Not started |  |  | 2014-10-05 | 2014-11-04
3RES-01 | Not Published to Access Seeker | VIC | 2015-06-26 | Not started |  |  | 2014-10-05 | 2014-11-04
4BUM-01 | Not Published to Access Seeker | QLD | 2015-06-27 | Not started |  |  | 2014-10-05 | 2014-11-04
4HWR-01 | Not Published to Access Seeker | QLD | 2015-06-27 | Not started |  |  | 2014-10-05 | 2014-11-04
4SHF-04 | Not Published to Access Seeker | QLD | 2015-06-27 | Not started |  |  | 2014-10-05 | 2014-11-04
4WUR-05 | Not Published to Access Seeker | QLD | 2016-08-13 | Not started |  |  | 2014-10-05 | 2014-11-04
5GUG-02 | Not Published to Access Seeker | SA | 2017-12-27 | Not started |  |  | 2014-10-05 | 2014-11-04
6ESP-02 | Not Published to Access Seeker | WA | 2015-06-27 | Not started |  |  | 2014-10-05 | 2014-11-04
7TAR-01 | Not Published to Access Seeker | TAS | 2017-06-30 | Not started |  |  | 2014-10-05 | 2014-11-04
9BLC-06 | Not Published to Access Seeker | ACT | 2015-06-27 | Not started |  |  | 2014-10-05 | 2014-11-04
5MOD-05 | Modbury | SA | 2013-12-14 | 2014-10-10 | 2014-08-16 | 2014-08-16 | 1Q-2015 | Commenced
3CRW-01 | Creswick | VIC | 2014-05-01 | 2014-05-07 | 2014-05-29 | 2014-05-29 | 3Q-2014 | Commenced
5PRO-04 | Prospect | SA | 2013-10-12 | 2014-06-12 | 2014-09-20 | 2014-09-20 | 3Q-2014 | Commenced
6MDR-05 | Mandurah | WA | 2013-10-12 | 2013-12-11 | 2014-04-23 | 2014-04-23 | 3Q-2014 | Not started
5PTA-03 | Port Augusta | SA | 2013-12-01 | 2014-07-25 | 2014-06-07 | 2014-06-07 | 3Q-2014 | Not started
5PTE-02 | Port Elliot and Victor Harbour | SA | 2014-12-10 | 2014-08-07 | 2014-07-03 | 2014-07-03 | 3Q-2014 | Not started
6APP-06 | Applecross | WA | 2013-12-14 | 2014-05-30 | 2014-07-04 | 2014-07-04 | 3Q-2014 | Not started
5STI-02 | Stirling | SA | 2013-10-31 | 2014-06-14 | 2014-08-24 | 2014-08-24 | 3Q-2014 | Not started
6SPT-04 | South Perth | WA | 2014-01-01 | 2014-05-08 | 2014-08-28 | 2014-08-28 | 3Q-2014 | Not started
8DRW-08 | Darwin | NT | 2013-12-14 | 2014-02-09 | 2014-10-21 | 2014-10-21 | 3Q-2014 | Not started
6SPT-03 | South Perth | WA | 2013-10-12 | 2013-12-11 | 2014-05-22 | 2014-05-22 | 4Q-2014 | Commenced
7BEV-04 | Bellerive | TAS | 2013-11-01 | 2014-02-28 | 2013-12-26 | 2013-12-26 | 4Q-2014 | Commenced
7BEV-03 | Bellerive | TAS | 2013-10-20 | 2014-03-02 | 2014-03-30 | 2014-03-30 | 4Q-2014 | Commenced
7BEV-02 | Bellerive | TAS | 2013-09-30 | 2013-11-02 | 2014-03-01 | 2014-03-01 | 4Q-2014 | Commenced
8CSU-02 | Casuarina | NT | 2014-07-01 | 2014-03-20 | 2014-01-29 | 2014-01-29 | 4Q-2014 | Commenced
6MDR-06 | Mandurah | WA | 2014-02-01 | 2013-11-17 | 2014-04-11 | 2014-04-11 | 4Q-2014 | Not started
6YND-01 | Yunderup | WA | 2013-10-12 | 2015-04-21 | 2014-06-06 | 2014-06-06 | 4Q-2014 | Not started
5PTA-02 | Port Augusta | SA | 2013-12-01 | 2014-08-10 | 2014-07-24 | 2014-07-24 | 4Q-2014 | Not started
2GOS-08 | Gosford | NSW | 2013-12-14 | 2014-03-02 | 2014-08-28 | 2014-08-28 | 4Q-2014 | Not started
5PTA-01 | Port Augusta | SA | 2013-12-01 | 2014-06-22 | 2014-12-05 | 2014-12-05 | 4Q-2014 | Not started
6MSP-04 | Meadow Springs | WA | 2013-11-01 | 2014-07-24 | 2014-12-13 | 2014-12-13 | 4Q-2014 | Not started
4TOB-08 | Toowoomba | QLD | 2014-01-24 | 2013-11-03 | 2014-03-01 | 2014-03-01 | Commenced | 2013-07-19
4TOB-07 | Toowoomba | QLD | 2014-01-24 | 2013-10-30 | 2014-03-12 | 2014-03-12 | Commenced | 2013-07-19
4CAI-04 | Cairns | QLD | 2014-08-01 | 2014-05-27 | 2014-03-02 | 2014-03-02 | Commenced | 2013-06-28
2PTH-05 | Penrith | NSW | 2014-01-24 | 2013-10-27 | 2014-01-08 | 2014-01-08 | Commenced | 2013-06-06
4CAI-05 | Cairns | QLD | 2014-08-01 | 2014-05-27 | 2014-04-24 | 2014-04-24 | Commenced | 2013-07-19
3SHP-03 | Shepparton | VIC | 2014-07-19 | 2014-04-21 | 2014-04-30 | 2014-04-30 | Commenced | 2013-07-26
3SHP-04 | Shepparton | VIC | 2014-07-19 | 2014-04-20 | 2014-04-30 | 2014-04-30 | Commenced | 2013-07-26
4ASH-03 | Ashmore | QLD | 2014-01-24 | 2014-02-06 | 2014-04-17 | 2014-04-17 | Commenced | 2013-07-12
4BDB-02 | Bundamba | QLD | 2014-01-24 | 2013-11-02 | 2014-05-18 | 2014-05-18 | Commenced | 2013-07-12
5FLN-01 | Flinders | SA | 2014-05-14 | 2014-09-02 | 2014-05-31 | 2014-05-31 | Commenced | 2013-07-19
4MKY-04 | Mackay | QLD | 2014-01-24 | 2013-12-04 | 2014-02-07 | 2014-02-07 | Commenced | 2013-06-24
3KAL-04 | Karingal | VIC | 2014-03-01 | 2014-03-27 | 2014-05-23 | 2014-05-23 | Commenced | 2013-07-26
9CVI-01 | Civic | ACT | 2014-01-24 | 2013-10-25 | 2014-03-25 | 2014-03-25 | Commenced | 2013-07-12
3CTN-02 | Carlton | VIC | 2014-01-24 | 2013-12-25 | 2014-04-10 | 2014-04-10 | Commenced | 2013-07-05
3CTN-08 | Carlton | VIC | 2014-02-14 | 2014-02-13 | 2014-04-16 | 2014-04-16 | Commenced | 2013-07-05
9CVI-02 | Civic | ACT | 2014-01-24 | 2013-11-01 | 2014-03-29 | 2014-03-29 | Commenced | 2013-07-26
2LID-01 | Lidcombe | NSW | 2013-06-15 | 2013-09-15 | 2013-07-30 | 2013-07-30 | IRRR | Commenced
2RCH-03 | Richmond | NSW | 2013-07-17 | 2013-09-01 | 2013-08-24 | 2013-08-24 | IRRR | Commenced
2BLK-02 | Blacktown | NSW | 2013-07-06 | 2013-12-21 | 2013-09-07 | 2013-09-07 | IRRR | Commenced
5MOD-01 | Modbury | SA | 2013-06-12 | 2014-01-02 | 2013-09-15 | 2013-09-15 | IRRR | Commenced
6GLT-02 | Geraldton | WA | 2013-07-21 | 2013-11-24 | 2013-10-01 | 2013-10-01 | IRRR | Commenced
8DRW-03 | Darwin | NT | 2014-03-30 | 2014-06-25 | 4Q-2014 | 4Q-2014 | IRRR | Commenced
5PRO-01 | Prospect | SA | 2013-05-09 | 2014-02-07 | 2013-09-15 | 2013-09-15 | IRRR | Commenced
5MOD-04 | Modbury | SA | 2014-05-15 | 2014-08-15 | 3Q-2014 | 3Q-2014 | IRRR | Commenced
6VIC-04 | Victoria Park | WA | 2013-09-11 | 2014-02-23 | 2014-01-01 | 2014-01-01 | IRRR | Commenced
6VIC-01 | Victoria Park | WA | 2013-09-04 | 2013-12-05 | 2014-01-01 | 2014-01-01 | IRRR | Commenced
6MDR-02 | Mandurah | WA | 2013-09-18 | 2014-01-23 | 2013-12-01 | 2013-12-01 | IRRR | Commenced
6VIC-03 | Victoria Park | WA | 2013-11-09 | 2013-12-19 | 2014-01-01 | 2014-01-01 | IRRR | Commenced
5MOD-02 | Modbury | SA | 2013-12-11 | 2014-02-08 | 2013-12-01 | 2013-12-01 | IRRR | Commenced
2ARM-06 | Armidale | NSW | 2013-05-01 | 2013-10-11 | 2013-07-30 | 2013-07-30 | IRRR | Commenced
2RCH-01 | Richmond | NSW | 2013-07-27 | 2013-08-15 | 2013-07-30 | 2013-07-30 | IRRR | Commenced
2RCH-02 | Richmond | NSW | 2013-05-25 | 2013-08-25 | 2013-07-30 | 2013-07-30 | IRRR | Commenced
2RIV-01 | Riverstone | NSW | 2013-07-27 | 2013-08-15 | 2013-07-30 | 2013-07-30 | IRRR | Commenced
6MDR-01 | Mandurah | WA | 2013-08-18 | 2013-09-12 | 2013-08-01 | 2013-08-01 | IRRR | Commenced
4GUL-04 | Gulliver | QLD | 2013-07-17 | 2013-10-22 | 2013-08-15 | 2013-08-15 | IRRR | Commenced
6VIC-02 | Victoria Park | WA | 2013-06-09 | 2013-08-24 | 2013-08-15 | 2013-08-15 | IRRR | Commenced
4GUL-02 | Gulliver | QLD | 2013-07-17 | 2014-02-03 | 2013-08-24 | 2013-08-24 | IRRR | Commenced
2BLK-01 | Blacktown | NSW | 2013-05-12 | 2013-11-07 | 2013-08-28 | 2013-08-28 | IRRR | Commenced
4GDN-01 | Goodna | QLD | 2013-06-27 | 2013-11-14 | 2013-08-30 | 2013-08-30 | IRRR | Commenced
4GDN-02 | Goodna | QLD | 2013-07-10 | 2014-01-23 | 2013-08-30 | 2013-08-30 | IRRR | Commenced
6GLT-01 | Geraldton | WA | 2013-05-29 | 2013-09-15 | 2013-08-30 | 2013-08-30 | IRRR | Commenced
4GUL-03 | Gulliver | QLD | 2013-06-21 | 2014-02-10 | 2013-10-01 | 2013-10-01 | IRRR | Commenced
5STI-01 | Stirling | SA | 2014-10-05 | 2014-09-13 | 1Q-2015 | 1Q-2015 | IRRR | Not started
2BLK-10 | Blacktown | NSW | 2014-05-14 | 2014-01-27 | 2014-03-16 | 2014-03-16 | Not started
7HOB-07 | Hobart | TAS | 2014-10-01 | 2014-07-07 | 2014-03-18 | 2014-03-18 | Not started
4ROT-02 | Rockhampton | QLD | 2014-01-24 | 2013-11-30 | 2014-03-22 | 2014-03-22 | Not started
7LAU-08 | Launceston | TAS | 2014-01-24 | 2014-05-22 | 2014-03-22 | 2014-03-22 | Not started
7SHL-01 | South Launceston | TAS | 2014-05-01 | 2013-12-18 | 2014-03-22 | 2014-03-22 | Not started
2PTH-07 | Penrith | NSW | 2014-04-15 | 2014-02-25 | 2014-03-23 | 2014-03-23 | Not started
9CVI-04 | Civic | ACT | 2014-02-14 | 2013-12-21 | 2014-03-23 | 2014-03-23 | Not started
2LIV-03 | Liverpool | NSW | 2014-05-14 | 2014-01-31 | 2014-03-28 | 2014-03-28 | Not started
2LIV-02 | Liverpool | NSW | 2014-05-14 | 2014-01-31 | 2014-03-29 | 2014-03-29 | Not started
4APL-06 | Aspley | QLD | 2014-01-24 | 2013-11-13 | 2014-03-30 | 2014-03-30 | Not started
4ASH-01 | Ashmore | QLD | 2014-01-24 | 2013-11-27 | 2014-03-30 | 2014-03-30 | Not started
4IPS-08 | Ipswich | QLD | 2014-04-15 | 2014-01-27 | 2014-04-02 | 2014-04-02 | Not started
9QBN-03 | Queanbeyan | ACT | 2014-07-01 | 2013-12-11 | 2014-04-03 | 2014-04-03 | Not started
2LIV-04 | Liverpool | NSW | 2014-04-15 | 2014-01-12 | 2014-04-05 | 2014-04-05 | Not started
2BLK-09 | Blacktown | NSW | 2014-04-15 | 2014-01-31 | 2014-04-09 | 2014-04-09 | Not started
4ASH-02 | Ashmore | QLD | 2014-01-24 | 2013-12-27 | 2014-04-10 | 2014-04-10 | Not started
9CVI-05 | Civic | ACT | 2014-04-15 | 2014-01-24 | 2014-04-11 | 2014-04-11 | Not started
2COR-08 | Corrimal | NSW | 2014-04-15 | 2014-03-01 | 2014-04-12 | 2014-04-12 | Not started
2MAI-07 | Maitland | NSW | 2014-04-15 | 2013-12-09 | 2014-04-12 | 2014-04-12 | Not started
2PTH-06 | Penrith | NSW | 2014-01-24 | 2013-11-01 | 2014-04-13 | 2014-04-13 | Not started
2WAG-03 | Wagga Wagga | NSW | 2014-09-01 | 2014-06-20 | 2014-04-15 | 2014-04-15 | Not started
2BLK-07 | Blacktown | NSW | 2014-05-14 | 2014-03-15 | 2014-04-17 | 2014-04-17 | Not started
4TOB-09 | Toowoomba | QLD | 2014-02-14 | 2013-11-20 | 2014-04-17 | 2014-04-17 | Not started
4SLA-02 | Slacks Creek | QLD | 2014-06-01 | 2014-04-22 | 2014-04-19 | 2014-04-19 | Not started
9QBN-04 | Queanbeyan | ACT | 2014-06-01 | 2014-06-06 | 2014-04-19 | 2014-04-19 | Not started
2LID-08 | Lidcombe | NSW | 2014-02-14 | 2013-12-21 | 2014-04-20 | 2014-04-20 | Not started
2WLG-06 | Wollongong | NSW | 2014-02-14 | 2013-11-27 | 2014-04-21 | 2014-04-21 | Not started
4BBE-01 | Bundaberg | QLD | 2014-08-01 | 2014-05-27 | 2014-04-23 | 2014-04-23 | Not started
2COR-04 | Corrimal | NSW | 2014-04-15 | 2014-03-01 | 2014-04-24 | 2014-04-24 | Not started
2LJT-06 | Long Jetty | NSW | 2014-03-01 | 2014-02-26 | 2014-04-24 | 2014-04-24 | Not started
2PTH-08 | Penrith | NSW | 2014-07-01 | 2014-06-19 | 2014-04-25 | 2014-04-25 | Not started
4SLA-01 | Slacks Creek | QLD | 2014-06-01 | 2014-03-27 | 2014-04-25 | 2014-04-25 | Not started
7HOB-08 | Hobart | TAS | 2014-10-01 | 2014-07-17 | 2014-04-25 | 2014-04-25 | Not started
7NWT-01 | Claremont | TAS | 2014-01-24 | 2013-12-18 | 2014-04-26 | 2014-04-26 | Not started
4GDN-08 | Goodna | QLD | 2014-02-14 | 2013-12-05 | 2014-04-27 | 2014-04-27 | Not started
9CVI-06 | Civic | ACT | 2014-04-15 | 2014-04-28 | 2014-04-27 | 2014-04-27 | Not started
9QBN-06 | Queanbeyan | ACT | 2014-04-15 | 2014-07-29 | 2014-04-27 | 2014-04-27 | Not started
2WAG-01 | Wagga Wagga | NSW | 2014-09-01 | 2014-06-20 | 2014-04-28 | 2014-04-28 | Not started
2WLG-05 | Wollongong | NSW | 2014-02-14 | 2013-12-28 | 2014-04-28 | 2014-04-28 | Not started
7SHL-02 | South Launceston | TAS | 2014-05-01 | 2014-02-01 | 2014-04-29 | 2014-04-29 | Not started
2WAG-02 | Wagga Wagga | NSW | 2014-09-01 | 2014-06-20 | 2014-04-30 | 2014-04-30 | Not started
4IPS-03 | Ipswich | QLD | 2014-05-01 | 2014-04-03 | 2014-04-30 | 2014-04-30 | Not started
2MAI-03 | Maitland | NSW | 2014-01-24 | 2013-12-06 | 2014-05-02 | 2014-05-02 | Not started
4KLG-07 | Kallangur and Petrie | QLD | 2014-04-15 | 2014-01-09 | 2014-05-02 | 2014-05-02 | Not started
4NDG-04 | Nudgee | QLD | 2014-05-01 | 2014-03-06 | 2014-05-02 | 2014-05-02 | Not started
4SLA-03 | Slacks Creek | QLD | 2014-06-01 | 2014-05-23 | 2014-05-02 | 2014-05-02 | Not started
4BBE-03 | Bundaberg | QLD | 2014-08-01 | 2014-05-31 | 2014-05-03 | 2014-05-03 | Not started
9CVI-03 | Civic | ACT | 2014-04-15 | 2014-01-26 | 2014-05-03 | 2014-05-03 | Not started
7HOB-09 | Hobart | TAS | 2014-07-19 | 2014-02-26 | 2014-05-06 | 2014-05-06 | Not started
2TEE-05 | Taree | NSW | 2014-01-24 | 2013-12-12 | 2014-05-08 | 2014-05-08 | Not started
6VIC-07 | Victoria Park | WA | 2014-03-01 | 2014-05-10 | 2014-05-08 | 2014-05-08 | Not started
3KEY-02 | Keysborough | VIC | 2014-01-24 | 2014-01-21 | 2014-05-10 | 2014-05-10 | Not started
4TNS-07 | Townsville | QLD | 2014-07-01 | 2014-05-13 | 2014-05-10 | 2014-05-10 | Not started
2GRN-02 | Grafton | NSW | 2014-07-01 | 2014-06-18 | 2014-05-15 | 2014-05-15 | Not started
3CTN-05 | Carlton | VIC | 2014-05-01 | 2014-03-29 | 2014-05-16 | 2014-05-16 | Not started
3KAL-02 | Karingal | VIC | 2014-03-01 | 2014-03-27 | 2014-05-16 | 2014-05-16 | Not started
3KAL-03 | Karingal | VIC | 2014-05-01 | 2014-03-27 | 2014-05-16 | 2014-05-16 | Not started
2LJT-09 | Long Jetty | NSW | 2014-04-15 | 2014-01-24 | 2014-05-17 | 2014-05-17 | Not started
2LJT-08 | Long Jetty | NSW | 2014-04-15 | 2014-02-13 | 2014-05-22 | 2014-05-22 | Not started
3BRU-07 | Brunswick | VIC | 2014-02-01 | 2014-02-13 | 2014-05-24 | 2014-05-24 | Not started
7NWT-02 | Claremont | TAS | 2014-01-24 | 2014-01-22 | 2014-05-24 | 2014-05-24 | Not started
3BRU-08 | Brunswick | VIC | 2014-02-01 | 2014-02-02 | 2014-05-31 | 2014-05-31 | Not started
3CBN-06 | Cranbourne | VIC | 2015-01-31 | 2014-07-03 | 2014-05-31 | 2014-05-31 | Not started
3CBN-04 | Cranbourne | VIC | 2014-10-01 | 2014-06-05 | 2014-06-01 | 2014-06-01 | Not started
4BBE-02 | Bundaberg | QLD | 2014-08-01 | 2014-05-27 | 2014-06-01 | 2014-06-01 | Not started
3FSR-04 | Footscray | VIC | 2014-08-01 | 2014-02-23 | 2014-06-04 | 2014-06-04 | Not started
5STI-03 | Stirling | SA | 2014-01-24 | 2014-06-21 | 2014-06-04 | 2014-06-04 | Not started
7NWT-06 | Claremont | TAS | 2014-08-08 | 2014-05-28 | 2014-06-04 | 2014-06-04 | Not started
7SHL-03 | South Launceston | TAS | 2014-06-01 | 2014-03-09 | 2014-06-04 | 2014-06-04 | Not started
2DBB-03 | Dubbo | NSW | 2014-05-26 | 2014-04-20 | 2014-06-07 | 2014-06-07 | Not started
6APP-07 | Applecross | WA | 2014-08-01 | 2014-04-21 | 2014-06-07 | 2014-06-07 | Not started
4ACO-06 | Ascot | QLD | 2014-05-14 | 2014-01-01 | 2014-06-08 | 2014-06-08 | Not started
4ASH-04 | Ashmore | QLD | 2014-07-19 | 2014-05-28 | 2014-06-08 | 2014-06-08 | Not started
4CAI-06 | Cairns | QLD | 2014-10-01 | 2014-06-28 | 2014-06-08 | 2014-06-08 | Not started
4TOB-10 | Toowoomba | QLD | 2014-07-19 | 2014-05-28 | 2014-06-08 | 2014-06-08 | Not started
6KAT-01 | Katanning | WA | 2014-09-01 | 2014-07-03 | 2014-06-09 | 2014-06-09 | Not started
6MDR-08 | Mandurah | WA | 2014-08-01 | 2014-04-22 | 2014-06-10 | 2014-06-10 | Not started
4APL-07 | Aspley | QLD | 2014-08-01 | 2014-06-26 | 2014-06-11 | 2014-06-11 | Not started
6MDR-09 | Mandurah | WA | 2014-04-01 | 2014-01-23 | 2014-06-11 | 2014-06-11 | Not started
3WER-01 | Werribee | VIC | 2014-06-01 | 2014-03-28 | 2014-06-12 | 2014-06-12 | Not started
3CBN-05 | Cranbourne | VIC | 2015-07-01 | 2014-07-03 | 2014-06-13 | 2014-06-13 | Not started
3KAL-05 | Karingal | VIC | 2014-05-01 | 2014-04-17 | 2014-06-13 | 2014-06-13 | Not started
4ACO-05 | Ascot | QLD | 2014-05-14 | 2013-12-19 | 2014-06-14 | 2014-06-14 | Not started
2RCH-07 | Richmond | NSW | 2014-04-15 | 2014-01-01 | 2014-06-15 | 2014-06-15 | Not started
4APL-08 | Aspley | QLD | 2014-09-01 | 2014-08-11 | 2014-06-16 | 2014-06-16 | Not started
4APL-09 | Aspley | QLD | 2014-08-01 | 2014-05-28 | 2014-06-16 | 2014-06-16 | Not started
4BDB-04 | Bundamba | QLD | 2014-08-01 | 2014-04-28 | 2014-06-16 | 2014-06-16 | Not started
4MKY-05 | Mackay | QLD | 2014-07-01 | 2014-04-27 | 2014-06-16 | 2014-06-16 | Not started
4NDG-05 | Nudgee | QLD | 2014-08-01 | 2014-04-20 | 2014-06-16 | 2014-06-16 | Not started
4NDG-06 | Nudgee | QLD | 2014-08-01 | 2014-05-21 | 2014-06-16 | 2014-06-16 | Not started
4ROT-04 | Rockhampton | QLD | 2014-10-01 | 2014-03-28 | 2014-06-16 | 2014-06-16 | Not started
6APP-08 | Applecross | WA | 2014-09-01 | 2014-07-01 | 2014-06-16 | 2014-06-16 | Not started
6CGE-05 | South Coogee | WA | 2015-06-01 | 2013-12-24 | 2014-06-16 | 2014-06-16 | Not started
4MKY-06 | Mackay | QLD | 2014-08-13 | 2014-07-16 | 2014-06-17 | 2014-06-17 | Not started
2WAG-04 | Wagga Wagga | NSW | 2014-08-01 | 2014-06-20 | 2014-06-18 | 2014-06-18 | Not started
9BLC-01 | Belconnen | ACT | 2014-07-01 | 2014-07-06 | 2014-06-18 | 2014-06-18 | Not started
9BLC-02 | Belconnen | ACT | 2014-09-01 | 2014-07-25 | 2014-06-18 | 2014-06-18 | Not started
3KEY-01 | Keysborough | VIC | 2014-02-14 | 2014-01-21 | 2014-06-19 | 2014-06-19 | Not started
4BDB-03 | Bundamba | QLD | 2014-10-01 | 2014-03-31 | 2014-06-19 | 2014-06-19 | Not started
6KOJ-01 | Kojonup | WA | 2014-08-01 | 2014-10-30 | 2014-06-19 | 2014-06-19 | Not started
4ACO-07 | Ascot | QLD | 2014-05-14 | 2014-01-31 | 2014-06-20 | 2014-06-20 | Not started
7NWT-03 | Claremont | TAS | 2014-01-27 | 2014-03-21 | 2014-06-21 | 2014-06-21 | Not started
7BEV-05 | Bellerive | TAS | 2014-11-01 | 2014-06-19 | 2014-06-23 | 2014-06-23 | Not started
6SPT-07 | South Perth | WA | 2014-10-01 | 2014-08-01 | 2014-06-25 | 2014-06-25 | Not started
3FSR-01 | Footscray | VIC | 2014-01-24 | 2013-12-22 | 2014-06-26 | 2014-06-26 | Not started
6CGE-04 | South Coogee | WA | 2014-02-14 | 2014-01-29 | 2014-06-27 | 2014-06-27 | Not started
6SPT-08 | South Perth | WA | 2014-04-23 | 2014-01-06 | 2014-06-27 | 2014-06-27 | Not started
2MYF-01 | Mayfield | NSW | 2014-07-01 | 2014-01-24 | 2014-06-28 | 2014-06-28 | Not started
7GEW-02 | George Town | TAS | 2014-04-15 | 2014-01-31 | 2014-06-28 | 2014-06-28 | Not started
2NWR-02 | Nowra-Bomaderry | NSW | 2014-07-19 | 2014-05-28 | 2014-06-29 | 2014-06-29 | Not started
3BRA-07 | Ballarat | VIC | 2014-06-01 | 2014-05-27 | 2014-07-01 | 2014-07-01 | Not started
3CTN-03 | Carlton | VIC | 2014-04-15 | 2014-02-28 | 2014-07-01 | 2014-07-01 | Not started
6VIC-09 | Victoria Park | WA | 2014-05-01 | 2014-01-04 | 2014-07-05 | 2014-07-05 | Not started
7BEV-06 | Bellerive | TAS | 2014-09-28 | 2014-05-28 | 2014-07-05 | 2014-07-05 | Not started
3FSR-05 | Footscray | VIC | 2014-04-26 | 2014-05-01 | 2014-07-08 | 2014-07-08 | Not started
3KEY-04 | Keysborough | VIC | 2014-07-01 | 2014-05-17 | 2014-07-10 | 2014-07-10 | Not started
4ACO-08 | Ascot | QLD | 2014-05-14 | 2014-01-31 | 2014-07-12 | 2014-07-12 | Not started
3FSR-07 | Footscray | VIC | 2014-07-19 | 2014-03-28 | 2014-07-15 | 2014-07-15 | Not started
7LEG-01 | Legana | TAS | 2014-08-01 | 2014-06-12 | 2014-07-15 | 2014-07-15 | Not started
4FRV-02 | Frenchville | QLD | 2014-11-01 | 2014-08-05 | 2014-07-17 | 2014-07-17 | Not started
7SHL-04 | South Launceston | TAS | 2014-07-01 | 2014-04-24 | 2014-07-18 | 2014-07-18 | Not started
2MAI-11 | Maitland | NSW | 2014-04-15 | 2014-02-12 | 2014-07-19 | 2014-07-19 | Not started
3BRA-08 | Ballarat | VIC | 2014-07-19 | 2014-07-01 | 2014-07-22 | 2014-07-22 | Not started
3SMR-08 | South Morang | VIC | 2014-07-01 | 2014-01-31 | 2014-07-23 | 2014-07-23 | Not started
6NTM-01 | Northam | WA | 2014-08-01 | 2014-06-02 | 2014-07-26 | 2014-07-26 | Not started
7NWT-04 | Claremont | TAS | 2014-06-01 | 2014-05-10 | 2014-07-26 | 2014-07-26 | Not started
3WER-02 | Werribee | VIC | 2014-07-19 | 2014-04-28 | 2014-08-02 | 2014-08-02 | Not started
3KEY-03 | Keysborough | VIC | 2014-05-01 | 2014-04-25 | 2014-08-05 | 2014-08-05 | Not started
2CYS-01 | City South | NSW | 2014-07-19 | 2014-03-21 | 2014-08-09 | 2014-08-09 | Not started
3FSR-06 | Footscray | VIC | 2014-07-19 | 2014-05-11 | 2014-08-09 | 2014-08-09 | Not started
5SFD-03 | Seaford | SA | 2014-12-01 | 2014-04-06 | 2014-08-16 | 2014-08-16 | Not started
2CYS-02 | City South | NSW | 2014-07-19 | 2014-03-21 | 2014-08-20 | 2014-08-20 | Not started
3TMN-06 | Tullamarine | VIC | 2014-08-01 | 2013-12-22 | 2014-08-21 | 2014-08-21 | Not started
5CPK-03 | St Marys | SA | 2014-10-01 | 2014-06-15 | 2014-08-21 | 2014-08-21 | Not started
2GBE-02 | Glebe | NSW | 2014-07-19 | 2014-01-24 | 2014-08-23 | 2014-08-23 | Not started
7LAU-09 | Launceston | TAS | 2014-04-15 | 2014-01-26 | 2014-08-23 | 2014-08-23 | Not started
5CPK-01 | St Marys | SA | 2014-10-01 | 2014-07-12 | 2014-08-24 | 2014-08-24 | Not started
7CRE-01 | Cremorne | TAS | 2014-07-19 | 2014-04-02 | 2014-08-26 | 2014-08-26 | Not started
5SFD-05 | Seaford | SA | 2014-12-01 | 2014-04-13 | 2014-08-28 | 2014-08-28 | Not started
5CPK-02 | St Marys | SA | 2014-05-01 | 2014-04-10 | 2014-08-30 | 2014-08-30 | Not started
5ALD-05 | Aldinga | SA | 2014-01-24 | 2014-07-10 | 2014-08-31 | 2014-08-31 | Not started
3KAL-01 | Karingal | VIC | 2014-07-25 | 2014-05-13 | 2014-09-02 | 2014-09-02 | Not started
3GEE-02 | Geelong | VIC | 2014-09-02 | 2014-06-26 | 2014-09-03 | 2014-09-03 | Not started
5MOD-07 | Modbury | SA | 2014-04-22 | 2014-06-20 | 2014-09-20 | 2014-09-20 | Not started
7NWT-05 | Claremont | TAS | 2014-07-19 | 2014-05-28 | 2014-09-23 | 2014-09-23 | Not started
5GAW-01 | Gawler | SA | 2014-02-01 | 2014-07-07 | 2014-09-26 | 2014-09-26 | Not started
5GAW-02 | Gawler | SA | 2014-09-01 | 2014-07-07 | 2014-09-26 | 2014-09-26 | Not started
3BAC-05 | Bacchus Marsh | VIC | 2014-09-13 | 2014-03-28 | 2014-09-30 | 2014-09-30 | Not started
7SHR-01 | South Arm | TAS | 2014-05-14 | 2014-03-02 | 2014-09-30 | 2014-09-30 | Not started
7LAU-10 | Launceston | TAS | 2014-07-01 | 2014-03-28 | 2014-10-04 | 2014-10-04 | Not started
7PON-01 | Pontville | TAS | 2014-07-19 | 2014-04-02 | 2014-10-05 | 2014-10-05 | Not started
2GBE-01 | Glebe | NSW | 2014-07-19 | 2014-04-20 | 2014-10-08 | 2014-10-08 | Not started
2PEA-02 | Peakhurst | NSW | 2014-07-19 | 2014-04-28 | 2014-10-08 | 2014-10-08 | Not started
7MGT-01 | Margate | TAS | 2014-07-19 | 2014-03-02 | 2014-10-12 | 2014-10-12 | Not started
2ROC-05 | Rockdale | NSW | 2014-10-18 | 2014-08-02 | 2014-10-23 | 2014-10-23 | Not started
6MSP-05 | Meadow Springs | WA | 2014-04-01 | 2014-07-05 | 2014-10-24 | 2014-10-24 | Not started
4GUL-07 | Gulliver | QLD | 2015-04-01 | 2014-11-29 | 2014-10-28 | 2014-10-28 | Not started
5GAW-03 | Gawler | SA | 2014-10-01 | 2014-07-07 | 2014-11-07 | 2014-11-07 | Not started
7WIN-01 | Windermere | TAS | 2014-08-01 | 2014-03-28 | 2014-11-08 | 2014-11-08 | Not started
2CYS-03 | City South | NSW | 2014-07-19 | 2014-02-26 | 2014-11-14 | 2014-11-14 | Not started
2GBE-03 | Glebe | NSW | 2014-07-19 | 2014-03-28 | 2014-11-21 | 2014-11-21 | Not started
2PEA-05 | Peakhurst | NSW | 2014-10-16 | 2014-08-28 | 2014-12-07 | 2014-12-07 | Not started
2ROC-06 | Rockdale | NSW | 2014-10-23 | 2014-09-02 | 2014-12-12 | 2014-12-12 | Not started
7SHL-05 | South Launceston | TAS | 2014-07-19 | 2014-09-18 | 2015-02-27 | 2015-02-27 | Not started
4SGI-01 | Springfield | QLD | 2015-07-01 | 2015-04-03 | 2015-03-29 | 2015-03-29 | Not started
4SGI-03 | Springfield | QLD | 2015-07-01 | 2015-03-19 | 2015-03-29 | 2015-03-29 | Not started
4SGI-06 | Springfield | QLD | 2015-07-01 | 2015-03-19 | 2015-03-29 | 2015-03-29 | Not started
7SHL-06 | South Launceston | TAS | 2014-07-29 | 2014-09-22 | 2015-04-04 | 2015-04-04 | Not started
2GOS-02 | Gosford | NSW | 2013-06-30 | 03-Apr-13 A | Live Site | Live Site | RRR
7HOB-02 | Hobart | TAS | 2013-06-30 | 25-May-13 A | Live Site | Live Site | RRR
9CRC-05 | Crace | ACT | 2013-10-01 | 2013-03-19 | Live Site | Live Site | RRR
9CRC-06 | Crace | ACT | 2013-07-15 | 2013-01-30 | Live Site | Live Site | RRR
2CFS-03 | Coffs Harbour | NSW | 2013-04-20 | 05-Jun-13 A | Live Site | Live Site | SRR | 2013-05-27
2GOS-01 | Gosford | NSW | 2013-10-01 | 28-May-13 A | Live Site | Live Site | SRR | 2013-05-28
3SMR-01 | South Morang | VIC | 2013-04-20 | 2013-07-04 | Live Site | Live Site | SRR | 2013-05-20
3SMR-04 | South Morang | VIC | 2013-06-01 | 13-Jun-13 A | Live Site | Live Site | SRR | 2013-05-20
4APL-02 | Aspley | QLD | 2013-07-15 | 13-Jun-13 A | Live Site | Live Site | SRR | 2013-06-07
4APL-03 | Aspley | QLD | 2013-07-31 | 21-May-13 A | Live Site | Live Site | SRR | 2013-05-21
4APL-04 | Aspley | QLD | 2013-07-31 | 21-May-13 A | Live Site | Live Site | SRR | 2013-05-20
7HOB-04 | Hobart | TAS | 2013-06-30 | 13-Jun-13 A | Live Site | Live Site | SRR | 2013-05-31
7LAU-01 | Launceston | TAS | 2013-03-31 | 05-Jun-13 A | Live Site | Live Site | SRR | 2013-05-20
7STH-02 | St Helens | TAS | 2013-04-30 | 2013-06-18 | Live Site | Live Site | SRR | 2013-06-11
8DRW-01 | Darwin | NT | Live Site | IRRR | 2013-05-28 | 2013-05-28
3BAC-01 | Bacchus Marsh | VIC | Live Site | IRRR | 2013-06-12 | 2013-06-12 |  | 2013-07-18
2SAW-01 | Sawtell | NSW | Live Site | IRRR | 2013-06-17 | 2013-06-17
2KIA-03 | Kiama | NSW | Live Site | IRRR | 2013-06-18 | 2013-06-18
2PTH-01 | Penrith | NSW | Live Site | IRRR | 2013-06-19 | 2013-06-19
4TOB-02 | Toowoomba | QLD | Live Site | IRRR | 2013-06-20 | 2013-06-20
2KIA-02 | Kiama | NSW | Live Site | IRRR | 2013-06-28 | 2013-06-28 |  | 2013-08-06
2RCH-04 | Richmond | NSW | Live Site | IRRR | 2013-06-28 | 2013-06-28 |  | 2013-08-06
8DRW-02 | Darwin | NT | Live Site | IRRR | 2013-06-28 | 2013-06-28
2ALB-01 | Not Published to Access Seeker | NSW | 2014-09-02 | 2015-02-05 | Not started | Not started |  | 2013-10-19
2ALB-02 | Not Published to Access Seeker | NSW | 2014-10-02 | 2014-10-20 | Not started | Not started |  | 2014-01-29
2BIN-01 | Not Published to Access Seeker | NSW | 2014-10-03 |  | Not started | Not started
2BLK-08 | Not Published to Access Seeker | NSW | 2014-03-24 | 2014-12-22 | Not started | Not started |  | 2014-04-01
2BLK-11 | Not Published to Access Seeker | NSW | 2014-09-28 | 2014-07-26 | Not started | Not started |  | 2013-11-03
2BLK-12 | Not Published to Access Seeker | NSW | 2014-09-28 | 2014-08-21 | Not started | Not started |  | 2013-11-29
2BUR-10 | Not Published to Access Seeker | NSW | 2018-03-10 |  | Not started | Not started
2CAS-01 | Not Published to Access Seeker | NSW | 2014-07-29 | 2014-07-22 | Not started | Not started |  | 2013-10-30
2CAS-02 | Not Published to Access Seeker | NSW | 2014-07-29 | 2014-08-21 | Not started | Not started |  | 2013-11-29
2CAS-03 | Not Published to Access Seeker | NSW | 2014-08-02 | 2014-11-21 | Not started | Not started |  | 2014-03-01
2CBT-04 | Campbelltown | NSW | 2014-11-16 | 2014-06-18 | Not started | Not started |  | 2013-09-26
2CHA-01 | Not Published to Access Seeker | NSW | 2014-09-02 | 2014-07-26 | Not started | Not started |  | 2013-11-03
2CHA-02 | Not Published to Access Seeker | NSW | 2014-10-02 | 2014-08-21 | Not started | Not started |  | 2013-11-29
2CHA-03 | Not Published to Access Seeker | NSW | 2014-11-02 | 2014-10-21 | Not started | Not started |  | 2014-01-29
2COR-02 | Not Published to Access Seeker | NSW | 2014-05-30 | 2015-06-21 | Not started | Not started |  | 2014-09-29
2COR-03 | Not Published to Access Seeker | NSW | 2014-07-03 | 2014-11-21 | Not started | Not started |  | 2014-03-01
2COR-09 | Not Published to Access Seeker | NSW | 2014-08-28 | 2015-06-27 | Not started | Not started |  | 2014-10-05
2CYS-04 | Not Published to Access Seeker | NSW | 2014-06-28 |  | Not started | Not started
2CYS-05 | Not Published to Access Seeker | NSW | 2014-06-28 |  | Not started | Not started
2CYS-06 | Not Published to Access Seeker | NSW | 2014-06-28 |  | Not started | Not started
2CYS-07 | Not Published to Access Seeker | NSW | 2014-10-02 | 2014-11-21 | Not started | Not started |  | 2014-03-01
2CYS-08 | Not Published to Access Seeker | NSW | 2014-10-02 | 2015-04-21 | Not started | Not started |  | 2014-07-30
2CYS-09 | Not Published to Access Seeker | NSW | 2014-10-02 | 2015-06-21 | Not started | Not started |  | 2014-09-29
2DBB-01 | Not Published to Access Seeker | NSW | 2014-02-26 | 2015-04-21 | Not started | Not started |  | 2014-07-30
2DBB-02 | Not Published to Access Seeker | NSW | 2014-01-24 | 2014-09-28 | Not started | Not started |  | 2013-10-03
2DBB-04 | Not Published to Access Seeker | NSW | 2014-07-29 | 2014-07-23 | Not started | Not started |  | 2013-10-31
2DBB-05 | Not Published to Access Seeker | NSW | 2014-07-29 | 2014-07-22 | Not started | Not started |  | 2013-10-30
2DBB-06 | Not Published to Access Seeker | NSW | 2014-07-29 | 2014-08-21 | Not started | Not started |  | 2013-11-29
2GBE-04 | Not Published to Access Seeker | NSW | 2014-07-03 | 2014-07-18 | Not started | Not started |  | 2013-10-26
2GBE-05 | Not Published to Access Seeker | NSW | 2014-07-03 | 2014-09-21 | Not started | Not started |  | 2013-12-30
2GBE-06 | Not Published to Access Seeker | NSW | 2014-07-03 | 2014-12-22 | Not started | Not started |  | 2014-04-01
2GBE-07 | Not Published to Access Seeker | NSW | 2014-11-02 | 2015-04-21 | Not started | Not started |  | 2014-07-30
2GBE-08 | Not Published to Access Seeker | NSW | 2014-11-02 | 2015-06-27 | Not started | Not started |  | 2014-10-05
2GRA-08 | Not Published to Access Seeker | NSW | 2018-10-24 |  | Not started | Not started
2GRN-01 | Not Published to Access Seeker | NSW | 2014-06-18 | 2014-07-22 | Not started | Not started |  | 2013-10-30
2GRN-03 | Not Published to Access Seeker | NSW | 2014-06-18 | 2014-07-18 | Not started | Not started |  | 2013-10-26
2GRN-04 | Not Published to Access Seeker | NSW | 2014-06-18 | 2014-08-21 | Not started | Not started |  | 2013-11-29
2HAM-01 | Not Published to Access Seeker | NSW | 2014-08-28 | 2014-10-21 | Not started | Not started |  | 2014-01-29
2HAM-02 | Not Published to Access Seeker | NSW | 2014-08-28 | 2015-01-19 | Not started | Not started |  | 2014-04-29
2HAM-03 | Not Published to Access Seeker | NSW | 2014-08-02 | 2015-06-21 | Not started | Not started |  | 2014-09-29
2HOM-05 | Not Published to Access Seeker | NSW | 2014-04-30 | 2014-07-18 | Not started | Not started |  | 2013-10-26
2HOM-06 | Not Published to Access Seeker | NSW | 2014-02-01 | 2014-11-21 | Not started | Not started |  | 2014-03-01
2KNS-01 | Not Published to Access Seeker | NSW | 2014-05-28 | 2014-07-22 | Not started | Not started |  | 2013-10-30
2KNS-02 | Not Published to Access Seeker | NSW | 2014-05-28 | 2014-08-21 | Not started | Not started |  | 2013-11-29
2KNS-03 | Not Published to Access Seeker | NSW | 2014-06-28 | 2014-09-21 | Not started | Not started |  | 2013-12-30
2KNS-04 | Not Published to Access Seeker | NSW | 2014-10-02 | 2015-03-21 | Not started | Not started |  | 2014-06-29
2KNS-05 | Not Published to Access Seeker | NSW | 2014-11-02 | 2015-06-21 | Not started | Not started |  | 2014-09-29
2LIV-01 | Not Published to Access Seeker | NSW | 2016-08-27 |  | Not started | Not started
2LIV-05 | Not Published to Access Seeker | NSW | 2014-05-28 | 2014-10-21 | Not started | Not started |  | 2014-01-29
2LIV-06 | Not Published to Access Seeker | NSW | 2014-05-28 | 2014-12-22 | Not started | Not started |  | 2014-04-01
2LIV-07 | Not Published to Access Seeker | NSW | 2014-09-02 |  | Not started | Not started
2LIV-08 | Not Published to Access Seeker | NSW | 2014-09-02 |  | Not started | Not started
2LIV-09 | Not Published to Access Seeker | NSW | 2014-10-02 | 2015-02-19 | Not started | Not started |  | 2014-05-30
2LJT-10 | Not Published to Access Seeker | NSW | 2014-06-28 | 2014-09-21 | Not started | Not started |  | 2013-12-30
2MAI-01 | Not Published to Access Seeker | NSW | 2015-01-09 | 2015-04-21 | Not started | Not started |  | 2014-07-30
2MAI-02 | Not Published to Access Seeker | NSW | 2014-03-19 | 2014-09-21 | Not started | Not started |  | 2013-12-30
2MAI-04 | Not Published to Access Seeker | NSW | 2014-05-28 | 2014-08-21 | Not started | Not started |  | 2013-11-29
2MAI-05 | Not Published to Access Seeker | NSW | 2014-06-28 | 2014-09-21 | Not started | Not started |  | 2013-12-30
2MAI-06 | Not Published to Access Seeker | NSW | 2014-06-28 | 2015-01-19 | Not started | Not started |  | 2014-04-29
2MAI-08 | Not Published to Access Seeker | NSW | 2014-11-02 | 2015-06-21 | Not started | Not started |  | 2014-09-29
2MYF-02 | Not Published to Access Seeker | NSW | 2014-05-21 | 2014-07-22 | Not started | Not started |  | 2013-10-30
2MYF-03 | Not Published to Access Seeker | NSW | 2014-05-28 | 2014-08-21 | Not started | Not started |  | 2013-11-29
2MYF-04 | Not Published to Access Seeker | NSW | 2014-09-28 | 2014-11-21 | Not started | Not started |  | 2014-03-01
2MYF-05 | Not Published to Access Seeker | NSW | 2014-09-28 | 2015-03-21 | Not started | Not started |  | 2014-06-29
2NLT-01 | Not Published to Access Seeker | NSW | 2015-01-12 | 2015-01-29 | Not started | Not started |  | 2014-04-01
2NWR-01 | Not Published to Access Seeker | NSW | 2014-04-28 | 2014-12-22 | Not started | Not started |  | 2014-04-01
2NWR-03 | Not Published to Access Seeker | NSW | 2014-05-28 | 2014-07-16 | Not started | Not started |  | 2013-10-10
2NWR-04 | Not Published to Access Seeker | NSW | 2014-10-02 | 2014-09-21 | Not started | Not started |  | 2013-12-30
2NWR-05 | Not Published to Access Seeker | NSW | 2014-11-02 | 2015-03-21 | Not started | Not started |  | 2014-06-29
2PEA-01 | Not Published to Access Seeker | NSW | 2014-03-28 | 2015-06-21 | Not started | Not started |  | 2014-09-29
2PEA-03 | Not Published to Access Seeker | NSW | 2014-04-28 | 2015-02-19 | Not started | Not started |  | 2014-05-30
2PEA-04 | Not Published to Access Seeker | NSW | 2014-08-28 |  | Not started | Not started
2PEA-06 | Not Published to Access Seeker | NSW | 2014-08-28 | 2014-08-21 | Not started | Not started |  | 2013-11-29
2PEN-01 | Not Published to Access Seeker | NSW | 2014-10-02 | 2014-09-21 | Not started | Not started |  | 2013-12-30
2PEN-02 | Not Published to Access Seeker | NSW | 2014-11-02 | 2014-07-18 | Not started | Not started |  | 2013-10-26
2PTH-09 | Not Published to Access Seeker | NSW | 2014-07-10 | 2014-07-18 | Not started | Not started |  | 2013-10-26
2ROC-01 | Not Published to Access Seeker | NSW | 2014-04-28 |  | Not started | Not started
2ROC-02 | Not Published to Access Seeker | NSW | 2014-04-28 | 2015-05-21 | Not started | Not started |  | 2014-08-29
2ROC-03 | Not Published to Access Seeker | NSW | 2014-04-28 | 2015-06-27 | Not started | Not started |  | 2014-10-05
2ROC-04 | Not Published to Access Seeker | NSW | 2014-08-02 |  | Not started | Not started
2RYD-01 | Not Published to Access Seeker | NSW | 2014-06-28 | 2014-07-22 | Not started | Not started |  | 2013-10-30
2RYD-02 | Not Published to Access Seeker | NSW | 2014-06-28 | 2014-08-21 | Not started | Not started |  | 2013-11-29
2RYD-03 | Not Published to Access Seeker | NSW | 2014-07-29 | 2014-10-21 | Not started | Not started |  | 2014-01-29
2TAM-01 | Not Published to Access Seeker | NSW | 2014-10-02 | 2014-08-21 | Not started | Not started |  | 2013-11-29
2TAM-02 | Not Published to Access Seeker | NSW | 2014-11-02 | 2014-09-21 | Not started | Not started |  | 2013-12-30
2TAM-09 | Not Published to Access Seeker | NSW | 2014-03-26 |  | Not started | Not started
2TAM-10 | Not Published to Access Seeker | NSW | 2014-03-26 |  | Not started | Not started
2TEE-06 | Not Published to Access Seeker | NSW | 2014-04-20 | 2014-10-21 | Not started | Not started |  | 2014-01-29
2TRK-01 | The Rock | NSW | 2014-12-01 | 2014-06-18 | Not started | Not started |  | 2013-09-26
2WAG-05 | Not Published to Access Seeker | NSW | 2014-09-02 | 2014-08-21 | Not started | Not started |  | 2013-11-29
2WAG-06 | Not Published to Access Seeker | NSW | 2014-09-02 | 2014-11-21 | Not started | Not started |  | 2014-03-01
2WAG-07 | Not Published to Access Seeker | NSW | 2014-10-02 | 2014-12-22 | Not started | Not started |  | 2014-04-01
2WAG-08 | Not Published to Access Seeker | NSW | 2014-10-02 | 2015-01-19 | Not started | Not started |  | 2014-04-29
2WET-08 | Not Published to Access Seeker | NSW | 2018-12-26 |  | Not started | Not started
2WLG-07 | Not Published to Access Seeker | NSW | 2014-06-28 | 2014-07-26 | Not started | Not started |  | 2013-11-03
2WLG-08 | Not Published to Access Seeker | NSW | 2014-06-28 | 2014-12-22 | Not started | Not started |  | 2014-04-01
2WLG-09 | Not Published to Access Seeker | NSW | 2014-07-29 | 2015-02-19 | Not started | Not started |  | 2014-05-30
2WLG-10 | Not Published to Access Seeker | NSW | 2014-11-02 | 2015-03-21 | Not started | Not started |  | 2014-06-29
3BAC-04 | Not Published to Access Seeker | VIC | 2014-03-28 | 2014-07-29 | Not started | Not started |  | 2013-11-07
3BEN-01 | Not Published to Access Seeker | VIC | 2014-05-02 | 2014-08-20 | Not started | Not started |  | 2013-11-29
3BEN-02 | Not Published to Access Seeker | VIC | 2014-05-02 | 2014-11-20 | Not started | Not started |  | 2014-03-01
3BEN-03 | Not Published to Access Seeker | VIC | 2014-06-02 | 2014-12-21 | Not started | Not started |  | 2014-04-01
3BEN-04 | Not Published to Access Seeker | VIC | 2014-07-03 | 2015-02-18 | Not started | Not started |  | 2014-05-30
3BRA-09 | Not Published to Access Seeker | VIC | 2014-03-02 | 2014-07-21 | Not started | Not started |  | 2013-10-30
3CBN-01 | Not Published to Access Seeker | VIC | 2014-07-02 | 2014-09-20 | Not started | Not started |  | 2013-12-30
3CBN-02 | Not Published to Access Seeker | VIC | 2014-08-03 | 2015-06-27 | Not started | Not started |  | 2014-10-06
3CBN-03 | Not Published to Access Seeker | VIC | 2014-06-05 | 2015-02-18 | Not started | Not started |  | 2014-05-30
3CBN-07 | Not Published to Access Seeker | VIC | 2014-07-03 | 2014-07-29 | Not started | Not started |  | 2013-11-07
3CBN-08 | Not Published to Access Seeker | VIC | 2014-07-03 |  | Not started | Not started
3CSE-01 | Not Published to Access Seeker | VIC | 2019-06-25 | 2015-02-20 | Not started | Not started |  | 2014-05-30
3CTA-01 | Not Published to Access Seeker | VIC | 2014-09-02 | 2014-08-20 | Not started | Not started |  | 2013-11-29
3CTA-02 | Not Published to Access Seeker | VIC | 2014-10-02 | 2014-08-20 | Not started | Not started |  | 2013-11-29
3CTA-03 | Not Published to Access Seeker | VIC | 2014-11-02 | 2014-09-20 | Not started | Not started |  | 2013-12-30
3EXH-01 | Not Published to Access Seeker | VIC | 2014-04-29 | 2014-08-20 | Not started | Not started |  | 2013-11-29
3EXH-02 | Not Published to Access Seeker | VIC | 2014-04-29 | 2014-08-20 | Not started | Not started |  | 2013-11-29
3EXH-03 | Not Published to Access Seeker | VIC | 2014-05-21 | 2014-07-21 | Not started | Not started |  | 2013-10-30
3EXH-04 | Not Published to Access Seeker | VIC | 2014-05-25 | 2014-07-21 | Not started | Not started |  | 2013-10-30
3EXH-05 | Not Published to Access Seeker | VIC | 2014-08-27 | 2014-09-27 | Not started | Not started |  | 2014-01-06
3EXH-06 | Not Published to Access Seeker | VIC | 2014-09-15 | 2014-12-21 | Not started | Not started |  | 2014-04-01
3EXH-07 | Not Published to Access Seeker | VIC | 2014-11-02 | 2015-05-20 | Not started | Not started |  | 2014-08-29
3FSR-02 | Not Published to Access Seeker | VIC | 2015-07-07 | 2015-06-26 | Not started | Not started |  | 2014-10-05
3FSR-03 | Not Published to Access Seeker | VIC | 2015-11-14 |  | Not started | Not started
3FSR-08 | Not Published to Access Seeker | VIC | 2014-04-28 | 2014-09-20 | Not started | Not started |  | 2013-11-07
3FSR-09 | Not Published to Access Seeker | VIC | 2014-10-28 | 2015-01-18 | Not started | Not started |  | 2014-04-29
3GEE-01 | Not Published to Access Seeker | VIC | 2014-06-26 | 2014-09-27 | Not started | Not started |  | 2014-01-06
3GEE-03 | Not Published to Access Seeker | VIC | 2014-07-18 | 2014-09-20 | Not started | Not started |  | 2013-12-30
3GEE-04 | Not Published to Access Seeker | VIC | 2014-09-02 | 2015-03-20 | Not started | Not started |  | 2014-06-29
3GEE-05 | Not Published to Access Seeker | VIC | 2014-10-02 | 2015-04-26 | Not started | Not started |  | 2014-08-05
3GEE-06 | Not Published to Access Seeker | VIC | 2014-11-02 | 2015-06-26 | Not started | Not started |  | 2014-10-05
3HRS-01 | Not Published to Access Seeker | VIC | 2014-09-02 | 2014-11-20 | Not started | Not started |  | 2014-03-01
3HRS-02 | Not Published to Access Seeker | VIC | 2014-10-02 | 2015-03-27 | Not started | Not started |  | 2014-07-06
3HRS-03 | Not Published to Access Seeker | VIC | 2014-11-02 | 2015-06-20 | Not started | Not started |  | 2014-09-29
3KAL-06 | Not Published to Access Seeker | VIC | 2014-08-16 | 2014-07-21 | Not started | Not started |  | 2013-10-30
3KEY-05 | Not Published to Access Seeker | VIC | 2014-10-17 | 2014-09-27 | Not started | Not started |  | 2014-01-06
3KEY-06 | Not Published to Access Seeker | VIC | 2014-11-16 | 2014-09-27 | Not started | Not started |  | 2014-01-06
3KEY-07 | Not Published to Access Seeker | VIC | 2014-11-22 | 2014-10-20 | Not started | Not started |  | 2014-01-29
3KEY-08 | Not Published to Access Seeker | VIC | 2014-12-22 | 2014-10-20 | Not started | Not started |  | 2014-01-29
3KGP-01 | Not Published to Access Seeker | VIC | 2014-07-29 | 2014-08-20 | Not started | Not started |  | 2013-11-29
3KGP-02 | Not Published to Access Seeker | VIC | 2014-08-28 | 2014-10-20 | Not started | Not started |  | 2014-01-29
3KGP-03 | Not Published to Access Seeker | VIC | 2014-09-28 | 2014-12-21 | Not started | Not started |  | 2014-04-01
3LIL-01 | Not Published to Access Seeker | VIC | 2014-08-28 | 2014-09-26 | Not started | Not started |  | 2014-01-05
3LIL-02 | Not Published to Access Seeker | VIC | 2014-09-28 | 2015-02-24 | Not started | Not started |  | 2014-06-05
3LIL-03 | Not Published to Access Seeker | VIC | 2014-10-02 | 2015-06-26 | Not started | Not started |  | 2014-10-05
3MAI-01 | Not Published to Access Seeker | VIC | 2018-08-31 | 2020-05-02 | Not started | Not started |  | 2013-11-29
3MAI-02 | Not Published to Access Seeker | VIC | 2018-09-30 | 2020-05-02 | Not started | Not started |  | 2014-01-29
3MAI-03 | Not Published to Access Seeker | VIC | 2018-10-31 | 2020-05-02 | Not started | Not started |  | 2014-06-29
3MAI-04 | Not Published to Access Seeker | VIC | 2018-10-31 | 2020-05-02 | Not started | Not started |  | 2014-09-29
3MAI-05 | Not Published to Access Seeker | VIC | 2019-02-28 |  | Not started | Not started
3MLT-01 | Not Published to Access Seeker | VIC | 2014-09-21 | 2014-12-21 | Not started | Not started |  | 2014-04-01
3MLT-03 | Not Published to Access Seeker | VIC | 2015-01-21 | 2015-04-26 | Not started | Not started |  | 2014-08-05
3MLT-04 | Not Published to Access Seeker | VIC | 2014-10-02 |  | Not started | Not started
3MLT-10 | Not Published to Access Seeker | VIC | 2014-05-21 | 2014-06-21 | Not started | Not started |  | 2013-09-30
3MLT-11 | Not Published to Access Seeker | VIC | 2014-09-13 | 2014-10-20 | Not started | Not started |  | 2014-01-29
3MLT-12 | Not Published to Access Seeker | VIC | 2014-09-24 | 2014-11-20 | Not started | Not started |  | 2014-03-01
3SHP-01 | Not Published to Access Seeker | VIC | 2014-05-14 | 2014-07-21 | Not started | Not started |  | 2013-10-30
3SHP-02 | Not Published to Access Seeker | VIC | 2014-05-17 | 2015-01-18 | Not started | Not started |  | 2014-04-29
3SHP-05 | Not Published to Access Seeker | VIC | 2014-06-28 | 2014-07-21 | Not started | Not started |  | 2013-10-30
3SHP-06 | Not Published to Access Seeker | VIC | 2014-07-29 | 2014-10-20 | Not started | Not started |  | 2014-01-29
3SHP-07 | Not Published to Access Seeker | VIC | 2014-08-28 | 2014-11-20 | Not started | Not started |  | 2014-03-01
3SHP-08 | Not Published to Access Seeker | VIC | 2014-08-02 | 2015-01-18 | Not started | Not started |  | 2014-04-29
3STK-01 | Not Published to Access Seeker | VIC | 2014-07-30 | 2014-07-21 | Not started | Not started |  | 2013-10-30
3STK-02 | Not Published to Access Seeker | VIC | 2014-07-30 | 2014-08-20 | Not started | Not started |  | 2013-11-29
3STK-03 | Not Published to Access Seeker | VIC | 2014-07-22 | 2014-09-20 | Not started | Not started |  | 2013-12-30
3STK-04 | Not Published to Access Seeker | VIC | 2014-10-02 | 2015-01-18 | Not started | Not started |  | 2014-04-29
3STK-05 | Not Published to Access Seeker | VIC | 2014-11-02 | 2015-05-20 | Not started | Not started |  | 2014-08-29
3TAG-01 | Not Published to Access Seeker | VIC | 2014-09-09 | 2014-07-29 | Not started | Not started |  | 2013-11-07
3TAG-02 | Not Published to Access Seeker | VIC | 2014-10-10 | 2014-08-05 | Not started | Not started |  | 2013-11-14
3TAG-03 | Not Published to Access Seeker | VIC | 2014-11-02 | 2014-11-20 | Not started | Not started |  | 2014-03-01
3WER-03 | Not Published to Access Seeker | VIC | 2014-04-28 | 2014-07-05 | Not started | Not started |  | 2013-10-14
3WER-04 | Not Published to Access Seeker | VIC | 2014-04-28 | 2014-08-20 | Not started | Not started |  | 2013-11-29
3WER-05 | Not Published to Access Seeker | VIC | 2014-08-02 | 2015-02-18 | Not started | Not started |  | 2014-05-30
3WER-06 | Not Published to Access Seeker | VIC | 2014-08-02 | 2015-04-20 | Not started | Not started |  | 2014-07-30
3WER-07 | Not Published to Access Seeker | VIC | 2014-08-02 | 2015-06-20 | Not started | Not started |  | 2014-09-29
3WER-08 | Not Published to Access Seeker | VIC | 2014-09-02 |  | Not started | Not started
4AAR-12 | Not Published to Access Seeker | QLD | 2018-10-23 |  | Not started | Not started
4APL-10 | Not Published to Access Seeker | QLD | 2014-09-02 | 2014-10-21 | Not started | Not started |  | 2014-01-29
4APL-11 | Not Published to Access Seeker | QLD | 2014-10-02 | 2014-11-21 | Not started | Not started |  | 2014-03-01
4APL-12 | Not Published to Access Seeker | QLD | 2014-11-02 | 2014-12-22 | Not started | Not started |  | 2014-04-01
4ASH-05 | Not Published to Access Seeker | QLD | 2014-05-28 | 2014-07-22 | Not started | Not started |  | 2013-10-30
4ASH-06 | Not Published to Access Seeker | QLD | 2014-06-28 | 2014-09-28 | Not started | Not started |  | 2014-01-06
4ASH-07 | Not Published to Access Seeker | QLD | 2014-11-02 | 2015-02-19 | Not started | Not started |  | 2014-05-30
4AVO-02 | Not Published to Access Seeker | QLD | 2020-05-30 | 2020-03-13 | Not started | Not started |  | 2014-04-29
4BBE-04 | Not Published to Access Seeker | QLD | 2014-09-28 | 2014-08-21 | Not started | Not started |  | 2013-11-29
4BBE-05 | Not Published to Access Seeker | QLD | 2014-09-28 | 2014-09-28 | Not started | Not started |  | 2014-01-06
4BBE-06 | Not Published to Access Seeker | QLD | 2014-09-28 | 2014-10-21 | Not started | Not started |  | 2014-01-29
4BDB-05 | Not Published to Access Seeker | QLD | 2014-08-02 | 2014-10-21 | Not started | Not started |  | 2014-01-29
4BDB-06 | Not Published to Access Seeker | QLD | 2014-08-02 | 2014-12-22 | Not started | Not started |  | 2014-04-01
4BDB-07 | Not Published to Access Seeker | QLD | 2014-09-02 | 2015-01-19 | Not started | Not started |  | 2014-04-29
4BDB-08 | Not Published to Access Seeker | QLD | 2014-10-02 | 2015-04-21 | Not started | Not started |  | 2014-07-30
4CUR-06 | Not Published to Access Seeker | QLD | 2019-10-31 |  | Not started | Not started
4CUR-07 | Not Published to Access Seeker | QLD | 2020-02-28 |  | Not started | Not started
4EDG-01 | Not Published to Access Seeker | QLD | 2014-11-28 | 2014-12-03 | Not started | Not started |  | 2013-12-30
4EDG-02 | Not Published to Access Seeker | QLD | 2014-11-28 | 2014-12-03 | Not started | Not started |  | 2013-12-30
4EDG-03 | Not Published to Access Seeker | QLD | 2014-11-28 | 2015-01-19 | Not started | Not started |  | 2014-04-29
4FLA-01 | Not Published to Access Seeker | QLD | 2014-11-02 | 2014-11-21 | Not started | Not started |  | 2013-12-30
4FRE-01 | Not Published to Access Seeker | QLD | 2015-01-12 | 2015-02-18 | Not started | Not started |  | 2014-01-29
4FRE-02 | Not Published to Access Seeker | QLD | 2015-01-12 | 2015-02-18 | Not started | Not started |  | 2014-04-01
4FRV-01 | Not Published to Access Seeker | QLD | 2014-07-30 | 2014-07-22 | Not started | Not started |  | 2013-10-30
4FRV-03 | Not Published to Access Seeker | QLD | 2014-06-28 | 2014-08-28 | Not started | Not started |  | 2013-12-06
4FRV-04 | Not Published to Access Seeker | QLD | 2014-10-02 | 2014-11-21 | Not started | Not started |  | 2014-03-01
4FRV-05 | Not Published to Access Seeker | QLD | 2014-10-02 | 2014-12-22 | Not started | Not started |  | 2014-04-01
4FRV-06 | Not Published to Access Seeker | QLD | 2014-10-02 | 2015-02-19 | Not started | Not started |  | 2014-05-30
4HYP-01 | Not Published to Access Seeker | QLD | 2014-06-28 | 2014-08-21 | Not started | Not started |  | 2013-11-29
4IPS-05 | Not Published to Access Seeker | QLD | 2014-07-29 | 2014-08-28 | Not started | Not started |  | 2013-12-06
4IPS-06 | Not Published to Access Seeker | QLD | 2014-07-29 | 2014-09-21 | Not started | Not started |  | 2013-12-30
4IPS-07 | Not Published to Access Seeker | QLD | 2014-07-29 | 2014-09-21 | Not started | Not started |  | 2013-12-30
4IPS-09 | Not Published to Access Seeker | QLD | 2014-08-02 | 2015-01-19 | Not started | Not started |  | 2014-04-29
4KIR-07 | Not Published to Access Seeker | QLD | 2020-10-09 |  | Not started | Not started
4KIR-08 | Not Published to Access Seeker | QLD | 2020-10-09 |  | Not started | Not started
4KLG-03 | Not Published to Access Seeker | QLD | 2014-11-28 | 2015-01-19 | Not started | Not started |  | 2014-04-29
4KLG-05 | Not Published to Access Seeker | QLD | 2014-06-28 | 2014-08-28 | Not started | Not started |  | 2013-12-06
4KLG-06 | Not Published to Access Seeker | QLD | 2014-06-28 | 2014-11-21 | Not started | Not started |  | 2014-03-01
4KLG-08 | Not Published to Access Seeker | QLD | 2014-05-02 | 2014-08-21 | Not started | Not started |  | 2013-11-29
4NBR-01 | Not Published to Access Seeker | QLD | 2014-07-17 | 2014-12-22 | Not started | Not started |  | 2014-04-01
4NBR-02 | Not Published to Access Seeker | QLD | 2014-08-02 | 2015-04-21 | Not started | Not started |  | 2014-07-30
4NBR-03 | Not Published to Access Seeker | QLD | 2014-08-02 | 2015-05-21 | Not started | Not started |  | 2014-08-29
4NEW-11 | Not Published to Access Seeker | QLD | 2017-09-30 |  | Not started | Not started
4NIN-01 | Not Published to Access Seeker | QLD | 2014-08-28 | 2014-08-29 | Not started | Not started |  | 2013-11-29
4NIN-02 | Not Published to Access Seeker | QLD | 2014-09-28 | 2014-09-21 | Not started | Not started |  | 2013-12-30
4NIN-03 | Not Published to Access Seeker | QLD | 2014-10-02 | 2014-10-21 | Not started | Not started |  | 2014-01-29
4PRK-01 | Not Published to Access Seeker | QLD | 2014-11-02 | 2015-01-30 | Not started | Not started |  | 2013-12-30
4ROT-05 | Not Published to Access Seeker | QLD | 2014-07-29 | 2014-11-21 | Not started | Not started |  | 2014-03-01
4ROT-06 | Not Published to Access Seeker | QLD | 2014-07-29 |  | Not started | Not started
4SAR-01 | Not Published to Access Seeker | QLD | 2014-07-03 |  | Not started | Not started
4SFT-01 | Not Published to Access Seeker | QLD | 2014-07-03 |  | Not started | Not started
4SGI-04 | Not Published to Access Seeker | QLD | 2015-03-19 | 2015-03-29 | Not started | Not started |  | 2014-01-29
4SGI-05 | Not Published to Access Seeker | QLD | 2015-03-19 | 2015-03-29 | Not started | Not started |  | 2014-03-01
4SLA-04 | Not Published to Access Seeker | QLD | 2014-05-28 | 2014-07-22 | Not started | Not started |  | 2013-10-30
4SLA-05 | Not Published to Access Seeker | QLD | 2014-06-28 | 2014-08-28 | Not started | Not started |  | 2013-12-06
4SLA-06 | Not Published to Access Seeker | QLD | 2014-07-29 | 2014-09-21 | Not started | Not started |  | 2013-12-30
4SOP-01 | Not Published to Access Seeker | QLD | 2014-08-28 | 2014-10-21 | Not started | Not started |  | 2014-01-29
4SOP-02 | Not Published to Access Seeker | QLD | 2014-09-28 | 2014-12-22 | Not started | Not started |  | 2014-04-01
4SOP-03 | Not Published to Access Seeker | QLD | 2014-10-02 | 2014-12-22 | Not started | Not started |  | 2014-04-01
4TNS-08 | Not Published to Access Seeker | QLD | 2014-04-28 | 2014-08-21 | Not started | Not started |  | 2013-11-29
4TNS-09 | Not Published to Access Seeker | QLD | 2014-05-02 | 2014-08-28 | Not started | Not started |  | 2013-12-06
4TNS-10 | Not Published to Access Seeker | QLD | 2014-10-02 | 2014-11-21 | Not started | Not started |  | 2014-03-01
4TNS-11 | Not Published to Access Seeker | QLD | 2014-11-02 | 2015-04-21 | Not started | Not started |  | 2014-07-30
4TOB-11 | Not Published to Access Seeker | QLD | 2014-05-28 | 2014-07-22 | Not started | Not started |  | 2013-10-30
4TOB-12 | Not Published to Access Seeker | QLD | 2014-06-28 | 2014-09-21 | Not started | Not started |  | 2013-12-30
4WOB-01 | Not Published to Access Seeker | QLD | 2014-09-02 | 2014-11-21 | Not started | Not started |  | 2014-03-01
4WOB-02 | Not Published to Access Seeker | QLD | 2014-10-02 | 2014-12-22 | Not started | Not started |  | 2014-04-01
5BDW-01 | Not Published to Access Seeker | SA | 2014-12-08 | 2014-10-28 | Not started | Not started |  | 2013-12-30
5CPK-04 | Not Published to Access Seeker | SA | 2014-09-24 | 2014-08-21 | Not started | Not started |  | 2013-11-29
5CPK-05 | Not Published to Access Seeker | SA | 2014-10-25 | 2014-10-21 | Not started | Not started |  | 2014-01-29
5CPK-06 | Not Published to Access Seeker | SA | 2014-12-08 | 2014-10-21 | Not started | Not started |  | 2014-01-29
5CPK-07 | Not Published to Access Seeker | SA | 2014-11-02 | 2015-03-21 | Not started | Not started |  | 2014-06-29
5EDW-01 | Not Published to Access Seeker | SA | 2014-08-23 | 2014-07-19 | Not started | Not started |  | 2013-10-27
5EDW-02 | Not Published to Access Seeker | SA | 2014-09-22 | 2014-07-22 | Not started | Not started |  | 2013-10-30
5EDW-03 | Not Published to Access Seeker | SA | 2014-10-25 | 2014-09-21 | Not started | Not started |  | 2013-12-30
5EDW-04 | Not Published to Access Seeker | SA | 2014-10-02 | 2014-12-22 | Not started | Not started |  | 2014-04-01
5EDW-05 | Not Published to Access Seeker | SA | 2014-10-02 | 2015-04-21 | Not started | Not started |  | 2014-07-30
5EDW-06 | Not Published to Access Seeker | SA | 2014-11-02 | 2015-06-27 | Not started | Not started |  | 2014-10-05
5EZB-01 | Not Published to Access Seeker | SA | 2014-09-04 | 2014-07-19 | Not started | Not started |  | 2013-10-27
5EZB-02 | Not Published to Access Seeker | SA | 2014-09-08 | 2014-07-19 | Not started | Not started |  | 2013-10-27
5EZB-03 | Not Published to Access Seeker | SA | 2014-05-25 | 2014-07-19 | Not started | Not started |  | 2013-10-27
5EZB-04 | Not Published to Access Seeker | SA | 2014-08-28 | 2014-11-21 | Not started | Not started |  | 2014-03-01
5EZB-05 | Not Published to Access Seeker | SA | 2014-08-28 | 2015-01-19 | Not started | Not started |  | 2014-04-29
5EZB-06 | Not Published to Access Seeker | SA | 2014-09-28 | 2015-04-21 | Not started | Not started |  | 2014-07-30
5FLN-02 | Not Published to Access Seeker | SA | 2014-09-02 | 2014-07-22 | Not started | Not started |  | 2013-10-30
5FLN-03 | Not Published to Access Seeker | SA | 2014-10-02 | 2014-07-19 | Not started | Not started |  | 2013-10-27
5FRL-01 | Not Published to Access Seeker | SA | 2014-07-07 | 2014-10-12 | Not started | Not started |  | 2013-10-27
5GAW-04 | Not Published to Access Seeker | SA | 2014-10-25 | 2014-10-12 | Not started | Not started |  | 2013-10-30
5GAW-05 | Not Published to Access Seeker | SA | 2014-03-27 | 2014-10-12 | Not started | Not started |  | 2013-12-30
5GAW-06 | Not Published to Access Seeker | SA | 2014-11-27 | 2014-10-12 | Not started | Not started |  | 2013-12-30
5GAW-07 | Not Published to Access Seeker | SA | 2015-03-28 | 2014-12-22 | Not started | Not started |  | 2014-04-01
5GLW-01 | Not Published to Access Seeker | SA | 2014-05-28 | 2014-07-19 | Not started | Not started |  | 2013-10-27
5GLW-02 | Not Published to Access Seeker | SA | 2014-07-03 | 2014-07-22 | Not started | Not started |  | 2013-10-30
5GLW-03 | Not Published to Access Seeker | SA | 2014-10-28 | 2014-08-21 | Not started | Not started |  | 2013-11-29
5MCF-01 | Not Published to Access Seeker | SA | 2014-03-28 | 2014-07-19 | Not started | Not started |  | 2013-10-27
5MNN-01 | Not Published to Access Seeker | SA | 2014-10-09 | 2014-10-28 | Not started | Not started |  | 2014-01-29
5MOD-08 | Not Published to Access Seeker | SA | 2014-07-14 | 2014-12-11 | Not started | Not started |  | 2013-10-27
5MOD-09 | Not Published to Access Seeker | SA | 2014-07-13 | 2014-11-27 | Not started | Not started |  | 2013-10-27
5MOD-10 | Not Published to Access Seeker | SA | 2014-12-08 | 2014-10-21 | Not started | Not started |  | 2014-01-29
5MOD-11 | Not Published to Access Seeker | SA | 2015-01-07 | 2014-11-21 | Not started | Not started |  | 2014-03-01
5MYB-01 | Not Published to Access Seeker | SA | 2014-05-12 | 2014-10-21 | Not started | Not started |  | 2014-01-29
5MYB-02 | Not Published to Access Seeker | SA | 2014-05-12 | 2014-11-21 | Not started | Not started |  | 2014-03-01
5MYB-03 | Not Published to Access Seeker | SA | 2014-06-02 | 2014-11-21 | Not started | Not started |  | 2014-03-01
5PTE-04 | Not Published to Access Seeker | SA | 2014-07-21 | 2014-08-30 | Not started | Not started |  | 2013-10-27
5PTE-05 | Not Published to Access Seeker | SA | 2014-08-28 | 2014-10-17 | Not started | Not started |  | 2014-01-29
5QUR-01 | Not Published to Access Seeker | SA | 2014-08-28 | 2014-09-21 | Not started | Not started |  | 2013-12-30
5TWO-01 | Not Published to Access Seeker | SA | 2014-07-25 | 2014-10-12 | Not started | Not started |  | 2013-10-27
5WHL-01 | Not Published to Access Seeker | SA | 2014-10-07 | 2014-12-22 | Not started | Not started |  | 2014-04-01
5WHL-02 | Not Published to Access Seeker | SA | 2014-10-07 | 2015-01-19 | Not started | Not started |  | 2014-04-29
5WHL-03 | Not Published to Access Seeker | SA | 2014-11-02 | 2015-02-19 | Not started | Not started |  | 2014-05-30
6APP-09 | Not Published to Access Seeker | WA | 2014-02-08 | 2014-07-19 | Not started | Not started |  | 2013-10-27
6APP-10 | Not Published to Access Seeker | WA | 2014-06-02 | 2014-08-21 | Not started | Not started |  | 2013-11-29
6BAL-05 | Not Published to Access Seeker | WA | 2018-10-28 |  | Not started | Not started
6BAL-06 | Not Published to Access Seeker | WA | 2018-11-27 |  | Not started | Not started
6BGT-01 | Not Published to Access Seeker | WA | 2014-11-03 | 2015-04-21 | Not started | Not started |  | 2014-07-30
6BKH-01 | Not Published to Access Seeker | WA | 2014-05-15 | 2014-07-19 | Not started | Not started |  | 2013-10-27
6BRJ-01 | Not Published to Access Seeker | WA | 2014-08-02 | 2014-11-21 | Not started | Not started |  | 2014-03-01
6BSD-01 | Not Published to Access Seeker | WA | 2014-06-10 | 2014-07-22 | Not started | Not started |  | 2013-10-30
6BSD-02 | Not Published to Access Seeker | WA | 2014-07-03 | 2014-11-21 | Not started | Not started |  | 2014-03-01
6BSD-03 | Not Published to Access Seeker | WA | 2014-07-03 | 2015-01-19 | Not started | Not started |  | 2014-04-29
6BSD-09 | Not Published to Access Seeker | WA | 2015-12-28 |  | Not started | Not started
6BSD-10 | Not Published to Access Seeker | WA | 2016-05-27 |  | Not started | Not started
6CAN-01 | Not Published to Access Seeker | WA | 2014-07-03 | 2014-11-21 | Not started | Not started |  | 2014-03-01
6CAN-02 | Not Published to Access Seeker | WA | 2014-08-02 | 2014-12-22 | Not started | Not started |  | 2014-04-01
6CAN-03 | Not Published to Access Seeker | WA | 2014-08-02 | 2015-01-19 | Not started | Not started |  | 2014-04-29
6CER-01 | Not Published to Access Seeker | WA | 2015-02-10 | 2015-02-03 | Not started | Not started |  | 2014-04-01
6CGD-01 | Not Published to Access Seeker | WA | 2014-10-03 | 2015-05-21 | Not started | Not started |  | 2014-08-29
6CGE-02 | Not Published to Access Seeker | WA | 2014-08-19 | 2014-07-19 | Not started | Not started |  | 2013-10-27
6CND-01 | Not Published to Access Seeker | WA | 2014-05-13 | 2014-08-30 | Not started | Not started |  | 2013-11-29
6COI-01 | Not Published to Access Seeker | WA | 2014-12-06 | 2015-06-27 | Not started | Not started |  | 2014-10-05
6CVN-01 | Not Published to Access Seeker | WA | 2014-07-03 | 2015-04-21 | Not started | Not started |  | 2014-07-30
6DBL-01 | Not Published to Access Seeker | WA | 2014-08-02 | 2014-07-22 | Not started | Not started |  | 2013-10-30
6DBL-02 | Not Published to Access Seeker | WA | 2014-09-02 | 2014-10-21 | Not started | Not started |  | 2014-01-29
6DBL-03 | Not Published to Access Seeker | WA | 2014-09-02 | 2014-12-22 | Not started | Not started |  | 2014-04-01
6DNG-01 | Not Published to Access Seeker | WA | 2015-02-10 | 2015-02-03 | Not started | Not started |  | 2014-03-01
6GNO-01 | Not Published to Access Seeker | WA | 2014-05-15 | 2014-09-03 | Not started | Not started |  | 2013-10-27
6HER-01 | Not Published to Access Seeker | WA | 2014-08-20 | 2015-03-21 | Not started | Not started |  | 2014-06-29
6HER-02 | Not Published to Access Seeker | WA | 2014-08-20 | 2014-08-23 | Not started | Not started |  | 2013-10-27
6HER-03 | Not Published to Access Seeker | WA | 2014-08-20 | 2014-08-23 | Not started | Not started |  | 2013-10-27
6HER-04 | Not Published to Access Seeker | WA | 2014-10-02 | 2014-10-21 | Not started | Not started |  | 2014-01-29
6HER-05 | Not Published to Access Seeker | WA | 2014-10-02 | 2015-01-19 | Not started | Not started |  | 2014-04-29
6HIL-01 | Not Published to Access Seeker | WA | 2014-09-02 | 2015-06-21 | Not started | Not started |  | 2014-09-29
6HIL-02 | Not Published to Access Seeker | WA | 2014-10-02 |  | Not started | Not started
6HIL-03 | Not Published to Access Seeker | WA | 2014-11-02 |  | Not started | Not started
6HRV-01 | Not Published to Access Seeker | WA | 2014-07-03 | 2014-11-21 | Not started | Not started |  | 2014-03-01
6JUR-01 | Not Published to Access Seeker | WA | 2015-02-10 | 2015-02-03 | Not started | Not started |  | 2014-04-01
6KAM-01 | Not Published to Access Seeker | WA | 2014-08-02 | 2015-05-21 | Not started | Not started |  | 2014-08-29
6KBR-01 | Not Published to Access Seeker | WA | 2014-06-10 | 2014-08-30 | Not started | Not started |  | 2013-10-27
6KEL-01 | Not Published to Access Seeker | WA | 2014-02-08 | 2014-07-19 | Not started | Not started |  | 2013-10-27
6KEL-02 | Not Published to Access Seeker | WA | 2014-03-10 | 2014-07-19 | Not started | Not started |  | 2013-10-27
6KEL-03 | Not Published to Access Seeker | WA | 2014-04-10 | 2014-07-22 | Not started | Not started |  | 2013-10-30
6KEL-04 | Not Published to Access Seeker | WA | 2014-04-10 | 2014-07-19 | Not started | Not started |  | 2013-10-27
6KLB-01 | Not Published to Access Seeker | WA | 2014-04-10 | 2014-07-19 | Not started | Not started |  | 2013-10-27
6LEA-01 | Not Published to Access Seeker | WA | 2015-02-10 | 2015-02-03 | Not started | Not started |  | 2014-03-01
6LNC-01 | Not Published to Access Seeker | WA | 2015-02-10 | 2015-02-03 | Not started | Not started |  | 2014-04-29
6MBA-01 | Not Published to Access Seeker | WA | 2014-11-05 | 2015-06-21 | Not started | Not started |  | 2014-09-29
6MDI-01 | Not Published to Access Seeker | WA | 2014-06-10 | 2014-09-21 | Not started | Not started |  | 2013-12-30
6MDR-10 | Not Published to Access Seeker | WA | 2014-05-10 | 2014-08-21 | Not started | Not started |  | 2013-11-29
6MLU-01 | Not Published to Access Seeker | WA | 2014-07-03 | 2014-12-22 | Not started | Not started |  | 2014-04-01
6MRA-01 | Not Published to Access Seeker | WA | 2014-05-10 | 2014-07-19 | Not started | Not started |  | 2013-10-27
6NRG-01 | Not Published to Access Seeker | WA | 2014-08-02 | 2014-12-22 | Not started | Not started |  | 2014-04-01
6NTM-02 | Not Published to Access Seeker | WA | 2014-06-02 | 2014-07-19 | Not started | Not started |  | 2013-10-27
6PRE-01 | Not Published to Access Seeker | WA | 2014-03-10 | 2014-08-21 | Not started | Not started |  | 2013-11-29
6SCR-01 | Not Published to Access Seeker | WA | 2014-07-11 | 2014-08-15 | Not started | Not started |  | 2013-10-30
6SUB-01 | Not Published to Access Seeker | WA | 2014-05-10 |  | Not started | Not started
6SUB-02 | Not Published to Access Seeker | WA | 2014-05-10 | 2014-07-19 | Not started | Not started |  | 2013-10-27
6SUB-03 | Not Published to Access Seeker | WA | 2014-06-10 | 2014-09-21 | Not started | Not started |  | 2013-12-30
6SUB-04 | Not Published to Access Seeker | WA | 2014-10-02 | 2014-12-22 | Not started | Not started |  | 2014-04-01
6SUB-05 | Not Published to Access Seeker | WA | 2014-10-02 | 2015-03-21 | Not started | Not started |  | 2014-06-29
6SUB-06 | Not Published to Access Seeker | WA | 2014-11-02 | 2015-05-21 | Not started | Not started |  | 2014-08-29
6TOO-01 | Not Published to Access Seeker | WA | 2014-06-18 | 2014-07-19 | Not started | Not started |  | 2013-10-27
6VIC-10 | Not Published to Access Seeker | WA | 2014-05-10 | 2014-08-21 | Not started | Not started |  | 2013-11-29
6WGI-01 | Not Published to Access Seeker | WA | 2014-05-13 | 2014-08-30 | Not started | Not started |  | 2013-10-30
6WNG-01 | Not Published to Access Seeker | WA | 2014-04-10 | 2014-07-22 | Not started | Not started |  | 2013-10-30
6WRN-01 | Not Published to Access Seeker | WA | 2014-06-15 | 2014-07-19 | Not started | Not started |  | 2013-10-27
7BDP-01 | Not Published to Access Seeker | TAS | 2014-07-29 | 2014-09-20 | Not started | Not started |  | 2013-12-30
7BEL-01 | Not Published to Access Seeker | TAS | 2014-06-28 | 2014-08-27 | Not started | Not started |  | 2013-11-23
7CLT-01 | Not Published to Access Seeker | TAS | 2014-08-28 | 2014-09-20 | Not started | Not started |  | 2013-12-30
7DER-01 | Not Published to Access Seeker | TAS | 2015-01-30 | 2014-11-20 | Not started | Not started |  | 2014-03-01
7DER-02 | Not Published to Access Seeker | TAS | 2015-01-30 | 2014-12-21 | Not started | Not started |  | 2014-04-01
7DER-03 | Not Published to Access Seeker | TAS | 2015-01-30 | 2014-12-21 | Not started | Not started |  | 2014-04-01
7DER-04 | Not Published to Access Seeker | TAS | 2015-01-30 | 2015-01-18 | Not started | Not started |  | 2014-04-29
7ETD-01 | Not Published to Access Seeker | TAS | 2015-01-10 | 2014-10-20 | Not started | Not started |  | 2014-01-29
7ETD-02 | Not Published to Access Seeker | TAS | 2015-01-10 | 2014-11-20 | Not started | Not started |  | 2014-03-01
7EVA-01 | Not Published to Access Seeker | TAS | 2014-05-28 | 2014-07-29 | Not started | Not started |  | 2013-11-07
7EVA-02 | Not Published to Access Seeker | TAS | 2014-05-28 | 2014-08-20 | Not started | Not started |  | 2013-11-29
7HOB-10 | Not Published to Access Seeker | TAS | 2014-09-02 | 2014-10-20 | Not started | Not started |  | 2014-01-29
7HOB-11 | Not Published to Access Seeker | TAS | 2014-10-02 | 2014-11-20 | Not started | Not started |  | 2014-03-01
7NOL-01 | Not Published to Access Seeker | TAS | 2014-07-03 | 2015-01-18 | Not started | Not started |  | 2014-04-29
7NOL-02 | Not Published to Access Seeker | TAS | 2014-08-02 | 2015-02-18 | Not started | Not started |  | 2014-05-30
7NWT-07 | Not Published to Access Seeker | TAS | 2014-06-28 | 2014-07-05 | Not started | Not started |  | 2013-10-14
7NWT-08 | Not Published to Access Seeker | TAS | 2014-06-28 | 2014-08-05 | Not started | Not started |  | 2013-11-14
7NWT-09 | Not Published to Access Seeker | TAS | 2014-11-02 | 2014-12-21 | Not started | Not started |  | 2014-04-01
7PTS-01 | Not Published to Access Seeker | TAS | 2015-01-08 | 2015-03-20 | Not started | Not started |  | 2014-06-29
7RAO-01 | Not Published to Access Seeker | TAS | 2014-08-28 | 2015-04-20 | Not started | Not started |  | 2014-07-30
7WST-01 | Not Published to Access Seeker | TAS | 2014-06-28 | 2014-08-17 | Not started | Not started |  | 2013-11-26
8ALS-01 | Not Published to Access Seeker | NT | 2018-09-07 | 2015-03-07 | Not started | Not started |  | 2013-12-02
8ALS-02 | Not Published to Access Seeker | NT | 2018-09-07 | 2015-02-07 | Not started | Not started |  | 2013-12-01
8ALS-03 | Not Published to Access Seeker | NT | 2018-09-07 | 2015-02-07 | Not started | Not started |  | 2013-08-23
8ALS-04 | Not Published to Access Seeker | NT | 2018-09-07 | 2015-02-22 | Not started | Not started |  | 2013-10-27
8BRM-01 | Not Published to Access Seeker | NT | 2014-07-19 | 2014-09-21 | Not started | Not started |  | 2013-12-30
8CSU-06 | Not Published to Access Seeker | NT | 2013-12-24 | 2014-07-22 | Not started | Not started |  | 2013-10-30
8HDS-01 | Not Published to Access Seeker | NT | 2020-12-12 | 2020-12-17 | Not started | Not started |  | 2014-04-01
8HDS-02 | Not Published to Access Seeker | NT | 2020-12-12 | 2020-12-17 | Not started | Not started |  | 2014-04-29
8HDS-03 | Not Published to Access Seeker | NT | 2020-12-12 | 2020-12-17 | Not started | Not started |  | 2014-05-30
8HDS-04 | Not Published to Access Seeker | NT | 2020-12-12 | 2020-12-17 | Not started | Not started |  | 2014-06-29
8KTH-01 | Not Published to Access Seeker | NT | 2014-09-05 | 2014-10-15 | Not started | Not started |  | 2013-10-30
8KTH-02 | Not Published to Access Seeker | NT | 2014-08-21 |  | Not started | Not started
8NLN-01 | Not Published to Access Seeker | NT | 2014-10-30 | 2014-10-15 | Not started | Not started |  | 2013-12-30
8NOO-01 | Not Published to Access Seeker | NT | 2014-10-30 |  | Not started | Not started
8NTC-01 | Not Published to Access Seeker | NT | 2018-08-23 | 2014-10-21 | Not started | Not started |  | 2014-01-29
8NTC-02 | Not Published to Access Seeker | NT | 2018-08-23 | 2014-11-21 | Not started | Not started |  | 2014-03-01
8NTC-03 | Not Published to Access Seeker | NT | 2018-08-23 | 2014-11-21 | Not started | Not started |  | 2014-03-01
8TTC-01 | Not Published to Access Seeker | NT | 2018-09-07 | 2015-05-28 | Not started | Not started |  | 2013-10-27
9BLC-03 | Not Published to Access Seeker | ACT | 2014-05-28 | 2014-09-21 | Not started | Not started |  | 2013-12-30
9BLC-04 | Not Published to Access Seeker | ACT | 2014-09-02 | 2015-03-21 | Not started | Not started |  | 2014-06-29
9BLC-05 | Not Published to Access Seeker | ACT | 2014-10-02 | 2015-05-21 | Not started | Not started |  | 2014-08-29
9BON-01 | Not Published to Access Seeker | ACT | 2018-07-19 |  | Not started | Not started
9BON-02 | Not Published to Access Seeker | ACT | 2018-07-19 |  | Not started | Not started
9CRC-07 | Not Published to Access Seeker | ACT | 2014-09-04 | 2014-10-21 | Not started | Not started |  | 2014-01-29
9CRC-08 | Not Published to Access Seeker | ACT | 2014-08-18 | 2014-08-21 | Not started | Not started |  | 2013-11-29
9CRC-09 | Not Published to Access Seeker | ACT | 2014-08-11 | 2014-10-21 | Not started | Not started |  | 2014-01-29
9CVI-07 | Not Published to Access Seeker | ACT | 2014-08-02 | 2015-01-19 | Not started | Not started |  | 2014-04-29
9CVI-08 | Not Published to Access Seeker | ACT | 2014-08-02 | 2015-05-21 | Not started | Not started |  | 2014-08-29
9CVI-09 | Not Published to Access Seeker | ACT | 2014-09-02 | 2015-06-27 | Not started | Not started |  | 2014-10-05
9QBN-01 | Not Published to Access Seeker | ACT | 2014-04-17 |  | Not started | Not started
9QBN-02 | Not Published to Access Seeker | ACT | 2014-05-05 |  | Not started | Not started
9QBN-05 | Not Published to Access Seeker | ACT | 2014-07-29 | 2014-07-18 | Not started | Not started |  | 2013-10-26
9QBN-07 | Not Published to Access Seeker | ACT | 2014-08-28 | 2014-11-21 | Not started | Not started |  | 2014-03-01
9SCU-01 | Not Published to Access Seeker | ACT | 2019-05-23 | 2014-07-18 | Not started | Not started |  | 2013-10-26
9SCU-02 | Not Published to Access Seeker | ACT | 2019-05-23 | 2014-08-21 | Not started | Not started |  | 2013-11-29
9SCU-03 | Not Published to Access Seeker | ACT | 2019-05-23 | 2014-12-22 | Not started | Not started |  | 2014-04-01
9SCU-04 | Not Published to Access Seeker | ACT | 2019-05-23 | 2015-04-21 | Not started | Not started |  | 2014-07-30
2HOM-01 | Homebush | NSW | 2013-07-31 | Live Site | RRR | RRR
4CAI-01 | Cairns | QLD | 2013-10-31 | Live Site | RRR | RRR |  | 2013-07-09
4TOB-03 | Toowoomba | QLD | 2013-03-31 | Live Site | RRR | RRR
2AVA-01 | Not Published to Access Seeker | NSW |  | Not started
2AVA-02 | Not Published to Access Seeker | NSW |  | Not started
2AVA-03 | Not Published to Access Seeker | NSW |  | Not started
2BAN-01 | Not Published to Access Seeker | NSW |  | Not started
2BAN-02 | Not Published to Access Seeker | NSW |  | Not started
2BAN-03 | Not Published to Access Seeker | NSW |  | Not started
2BAN-04 | Not Published to Access Seeker | NSW |  | Not started
2BAN-05 | Not Published to Access Seeker | NSW |  | Not started
2BER-01 | Not Published to Access Seeker | NSW |  | Not started
2BER-02 | Not Published to Access Seeker | NSW |  | Not started
2BLG-01 | Not Published to Access Seeker | NSW |  | Not started
2BTL-01 | Not Published to Access Seeker | NSW |  | Not started
2CAM-06 | Not Published to Access Seeker | NSW |  | Not started
2CMO-01 | Not Published to Access Seeker | NSW |  | Not started
2CMO-02 | Not Published to Access Seeker | NSW |  | Not started
2CMO-03 | Not Published to Access Seeker | NSW |  | Not started
2CMO-04 | Not Published to Access Seeker | NSW |  | Not started
2CMO-05 | Not Published to Access Seeker | NSW |  | Not started
2CMO-06 | Not Published to Access Seeker | NSW |  | Not started
2CTW-01 | Not Published to Access Seeker | NSW |  | Not started
2DRG-01 | Not Published to Access Seeker | NSW |  | Not started
2ERP-01 | Not Published to Access Seeker | NSW |  | Not started
2ERP-02 | Not Published to Access Seeker | NSW |  | Not started
2ERP-03 | Not Published to Access Seeker | NSW |  | Not started
2ERP-04 | Not Published to Access Seeker | NSW |  | Not started
2ERP-05 | Not Published to Access Seeker | NSW |  | Not started
2ERP-06 | Not Published to Access Seeker | NSW |  | Not started
2HLS-03 | Not Published to Access Seeker | NSW |  | Not started
2HOW-01 | Not Published to Access Seeker | NSW |  | Not started
2JUE-01 | Not Published to Access Seeker | NSW |  | Not started
2LIV-12 | Not Published to Access Seeker | NSW |  | Not started
2MAN-01 | Not Published to Access Seeker | NSW |  | Not started
2MBT-01 | Not Published to Access Seeker | NSW |  | Not started
2MCL-01 | Not Published to Access Seeker | NSW |  | Not started
2MIR-06 | Not Published to Access Seeker | NSW |  | Not started
2MOS-05 | Not Published to Access Seeker | NSW |  | Not started
2MYF-06 | Not Published to Access Seeker | NSW |  | Not started
2RYD-07 | Not Published to Access Seeker | NSW |  | Not started
2RYD-08 | Not Published to Access Seeker | NSW |  | Not started
2RYD-09 | Not Published to Access Seeker | NSW |  | Not started
2STL-04 | Not Published to Access Seeker | NSW |  | Not started
2SUX-02 | Not Published to Access Seeker | NSW |  | Not started
2TAH-02 | Not Published to Access Seeker | NSW |  | Not started
2TAH-03 | Not Published to Access Seeker | NSW |  | Not started
2YMB-01 | Not Published to Access Seeker | NSW |  | Not started
2YMB-02 | Not Published to Access Seeker | NSW |  | Not started
2YMB-03 | Not Published to Access Seeker | NSW |  | Not started
3BRF-01 | Not Published to Access Seeker | VIC |  | Not started
3BUR-01 | Not Published to Access Seeker | VIC |  | Not started
3BUR-02 | Not Published to Access Seeker | VIC |  | Not started
3BUR-03 | Not Published to Access Seeker | VIC |  | Not started
3BUR-04 | Not Published to Access Seeker | VIC |  | Not started
3BWK-01 | Not Published to Access Seeker | VIC |  | Not started
3BWK-02 | Not Published to Access Seeker | VIC |  | Not started
3BWK-03 | Not Published to Access Seeker | VIC |  | Not started
3BWK-04 | Not Published to Access Seeker | VIC |  | Not started
3HAW-03 | Not Published to Access Seeker | VIC |  | Not started
3HUR-01 | Not Published to Access Seeker | VIC |  | Not started
3HUR-02 | Not Published to Access Seeker | VIC |  | Not started
3HUR-03 | Not Published to Access Seeker | VIC |  | Not started
3KEY-09 | Not Published to Access Seeker | VIC |  | Not started
3KYN-01 | Not Published to Access Seeker | VIC |  | Not started
3MOO-02 | Not Published to Access Seeker | VIC |  | Not started
3TNB-02 | Not Published to Access Seeker | VIC |  | Not started
3WIR-01 | Not Published to Access Seeker | VIC |  | Not started
3WIR-02 | Not Published to Access Seeker | VIC |  | Not started
3WIR-03 | Not Published to Access Seeker | VIC |  | Not started
3WLN-01 | Not Published to Access Seeker | VIC |  | Not started
3WLN-02 | Not Published to Access Seeker | VIC |  | Not started
3WOR-01 | Not Published to Access Seeker | VIC |  | Not started
4BOO-01 | Not Published to Access Seeker | QLD |  | Not started
4BWE-01 | Not Published to Access Seeker | QLD |  | Not started
4BWE-02 | Not Published to Access Seeker | QLD |  | Not started
4CKT-01 | Not Published to Access Seeker | QLD |  | Not started
4CLI-01 | Not Published to Access Seeker | QLD |  | Not started
4FHL-01 | Not Published to Access Seeker | QLD |  | Not started
4FHL-02 | Not Published to Access Seeker | QLD |  | Not started
4FHL-03 | Not Published to Access Seeker | QLD |  | Not started
4FHL-04 | Not Published to Access Seeker | QLD |  | Not started
4GAT-01 | Not Published to Access Seeker | QLD |  | Not started
4GAT-02 | Not Published to Access Seeker | QLD |  | Not started
4GAT-03 | Not Published to Access Seeker | QLD |  | Not started
4GUL-08 | Not Published to Access Seeker | QLD |  | Not started
4GUL-09 | Not Published to Access Seeker | QLD |  | Not started
4KLC-01 | Not Published to Access Seeker | QLD |  | Not started
4LAM-03 | Not Published to Access Seeker | QLD |  | Not started
4LND-01 | Not Published to Access Seeker | QLD |  | Not started
4NEW-05 | Not Published to Access Seeker | QLD |  | Not started
4NEW-06 | Not Published to Access Seeker | QLD |  | Not started
4POM-01 | Not Published to Access Seeker | QLD |  | Not started
4POM-02 | Not Published to Access Seeker | QLD |  | Not started
4PWT-01 | Not Published to Access Seeker | QLD |  | Not started
4SGI-02 | Not Published to Access Seeker | QLD |  | Not started
4SHF-05 | Not Published to Access Seeker | QLD |  | Not started
4TQA-01 | Not Published to Access Seeker | QLD |  | Not started
4TQA-02 | Not Published to Access Seeker | QLD |  | Not started
4WDF-01 | Not Published to Access Seeker | QLD |  | Not started
4WUR-06 | Not Published to Access Seeker | QLD |  | Not started
5GUG-03 | Not Published to Access Seeker | SA |  | Not started
5GUG-04 | Not Published to Access Seeker | SA |  | Not started
5GUG-05 | Not Published to Access Seeker | SA |  | Not started
5GUG-06 | Not Published to Access Seeker | SA |  | Not started
6DRB-01 | Not Published to Access Seeker | WA |  | Not started
6ESP-03 | Not Published to Access Seeker | WA |  | Not started
6JDL-01 | Not Published to Access Seeker | WA |  | Not started
6JDL-02 | Not Published to Access Seeker | WA |  | Not started
6JDL-03 | Not Published to Access Seeker | WA |  | Not started
6LWC-01 | Not Published to Access Seeker | WA |  | Not started
6MDJ-01 | Not Published to Access Seeker | WA |  | Not started
6QIN-01 | Not Published to Access Seeker | WA |  | Not started
6QIN-02 | Not Published to Access Seeker | WA |  | Not started
6QIN-03 | Not Published to Access Seeker | WA |  | Not started
6QIN-04 | Not Published to Access Seeker | WA |  | Not started
6QIN-05 | Not Published to Access Seeker | WA |  | Not started
6RKH-04 | Not Published to Access Seeker | WA |  | Not started
9BLC-07 | Not Published to Access Seeker | ACT |  | Not started
9KBA-05 | Not Published to Access Seeker | ACT |  | Not started
9KBA-06 | Not Published to Access Seeker | ACT |  | Not started
9QBN-10 | Not Published to Access Seeker | ACT |  | Not started
9SCU-07 | Not Published to Access Seeker | ACT |  | Not started
9SCU-08 | Not Published to Access Seeker | ACT |  | Not started